## master data
BASELINE
Eixo | Grupo | Marco \ Entrega | TAREFA | FORNECEDOR | RESPONSÁVEL | PRIORIDADE | STATUS | DATA INÍCIO | DATA FIM | DURAÇÃO | PREDECESSORES | PROGRESSO O que andou (ou travou) nos últimos dias | ENCAMINHAMENTOS Orientações da gerência | FOYER | ÁREA 0 (pinguela) | ÁREA 1 (diversidade) | ÁREA 2 (oralidade e tecnologias) | ÁREA 3 (aturá e feira) | ÁREA 4 (crises) | ÁREA 5 (bem viver) | MEZANINO | EXPOSIÇÃO TEMPORÁRIA | LOJA | ÁREA EXTERNA DO MUSEU | ÁREAS COMUNS (BANHEIROS, CIRCULAÇÕES ETC.)
|  |  | INSTITUCIONAL |  |  | Alta | Em Andamento | 2026-04-01 | 2028-12-31 | 1005
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS |  | CAPTAÇÃO DE RECURSOS |  | Iago Gonçalves Pereira |  | Em Andamento | 2026-04-01 | 2026-07-15 | 105
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 1] PLANEJAMENTO E NEGOCIAÇÕES INSTITUCIONAIS | [PREP 1] PLANEJAMENTO E NEGOCIAÇÕES INSTITUCIONAIS |  | Iago Gonçalves Pereira |  | Em Andamento | 2026-04-01 | 2026-04-30 | 29
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 1] PLANEJAMENTO E NEGOCIAÇÕES INSTITUCIONAIS | Definição do modelo de governança do projeto |  | Iago Gonçalves Pereira | Média | Feito | 2026-04-01 | 2026-04-15 | 14
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 1] PLANEJAMENTO E NEGOCIAÇÕES INSTITUCIONAIS | Negociações institucionais com parceiros e patrocinadores |  | Iago Gonçalves Pereira |  | Em Andamento | 2026-04-01 | 2026-04-30 | 29
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 1] PLANEJAMENTO E NEGOCIAÇÕES INSTITUCIONAIS | Planejamento da captação e gestão de recursos (verba direta e incentivada) |  | Iago Gonçalves Pereira |  | Em Andamento | 2026-04-01 | 2026-04-30 | 29
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 2] RECEBIMENTO DE RECURSOS E CONTRATAÇÕES INICIAIS | [PREP 2] RECEBIMENTO DE RECURSOS E CONTRATAÇÕES INICIAIS |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2026-05-01 | 2026-06-30 | 60
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 2] RECEBIMENTO DE RECURSOS E CONTRATAÇÕES INICIAIS | Recebimento do recurso de verba direta |  | Tatiana Paulino de Azevedo | Baixa | A Iniciar | 2026-05-01 | 2026-05-15 | 14
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 2] RECEBIMENTO DE RECURSOS E CONTRATAÇÕES INICIAIS | Recebimento dos recursos incentivados |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2026-07-01 | 2026-07-15 | 14
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 2] RECEBIMENTO DE RECURSOS E CONTRATAÇÕES INICIAIS | Elaboração e publicação de editais para contratações de projetos |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2026-05-01 | 2026-06-15 | 45
INSTITUCIONAL | CAPTAÇÃO DE RECURSOS | [PREP 2] RECEBIMENTO DE RECURSOS E CONTRATAÇÕES INICIAIS | Contratação de equipes: arquitetura, expografia, conteúdo |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2026-06-01 | 2026-06-30 | 29
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS |  | FORMALIZAÇÕES INSTITUCIONAIS |  | Iago Gonçalves Pereira |  | Em Andamento
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Aprovações INEPAC | Aprovações INEPAC |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Aprovações INEPAC | Estudo das portarias |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Aprovações INEPAC | Alinhamento institucional com arquitetura, engenharia e facilities |  | Iago Gonçalves Pereira |  | A Iniciar
| FORMALIZAÇÕES INSTITUCIONAIS | Aprovações INEPAC | Protocolo de documentos |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Esdi | Esdi |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Esdi | Alinhamento inicial |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Esdi | Definição de contrapartidas |  | Iago Gonçalves Pereira |  | A Iniciar
| FORMALIZAÇÕES INSTITUCIONAIS | Esdi | Plano de ação |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Governança Externa | Governança Externa |  | Iago Gonçalves Pereira |  | A Iniciar
INSTITUCIONAL | FORMALIZAÇÕES INSTITUCIONAIS | Governança Externa | Estruturação de comitê de implantação |  | Iago Gonçalves Pereira |  | A Iniciar
PROJETOS | PROJETOS |  | PROJETOS |  | Valeria Ferro |  | A Iniciar
PROJETOS | PROJETOS DE ARQUITETURA |  | PROJETOS DE ARQUITETURA |  | Valeria Ferro |  | A Iniciar | 2026-07-01 | 2027-03-31 | 273
PROJETOS | PROJETOS DE ARQUITETURA | [ARQ 1] ENTREGA DA OBRA PELA PREFEITURA* *O início das obras civis só começa após esta entrega | [ARQ 1] ENTREGA DA OBRA PELA PREFEITURA* *O início das obras civis só começa após esta entrega |  | Valeria Ferro |  | A Iniciar | 2026-07-01 | 2026-12-31 | 183
PROJETOS | PROJETOS DE ARQUITETURA | [ARQ 1] ENTREGA DA OBRA PELA PREFEITURA* *O início das obras civis só começa após esta entrega | Reuniões de acompanhamento semanais com Tensor/Riourbe/SMI |  | Valeria Ferro |  | A Iniciar | 2026-07-01 | 2026-12-31 | 183
PROJETOS | PROJETOS DE ARQUITETURA | [ARQ 1] ENTREGA DA OBRA PELA PREFEITURA* *O início das obras civis só começa após esta entrega | Monitoramento de prazos e entrega do edifício |  | Valeria Ferro |  | A Iniciar | 2026-07-01 | 2026-12-31 | 183
PROJETOS | PROJETOS DE ARQUITETURA | [ARQ 1] ENTREGA DA OBRA PELA PREFEITURA* *O início das obras civis só começa após esta entrega | Recebimento formal do edifício do Automóvel Clube |  | Valeria Ferro |  | A Iniciar | 2026-12-01 | 2026-12-31 | 30
PROJETOS | PROJETOS DE ARQUITETURA | [ARQ 2] PROJETOS DE ARQUITETURA E COMPLEMENTARES | [ARQ 2] PROJETOS DE ARQUITETURA E COMPLEMENTARES |  | Valeria Ferro |  | A Iniciar | 2026-07-01 | 2027-03-31 | 273
PROJETOS | PROJETOS DE ARQUITETURA | [ARQ 2] PROJETOS DE ARQUITETURA E COMPLEMENTARES | Projeto executivo de arquitetura e complementares (estrutural, elétrico, hidráulico, HVAC, A/CSPCI) |  | Valeria Ferro |  | A Iniciar | 2026-07-01 | 2027-03-31 | 273
PROJETOS | OBRAS CIVIS* |  | OBRAS CIVIS* |  | Valeria Ferro |  | A Iniciar | 2027-03-01 | 2028-03-01 | 366
PROJETOS | OBRAS CIVIS* | [OBR 1] Execução das obras civis - PRÉDIO PRINCIPAL | [OBR 1] Execução das obras civis - PRÉDIO PRINCIPAL |  | Valeria Ferro |  | A Iniciar | 2027-03-01 | 2028-03-01 | 366
PROJETOS | OBRAS CIVIS* | [OBR 1] Execução das obras civis - PRÉDIO PRINCIPAL |  |  | Valeria Ferro |  | A Iniciar
PROJETOS | OBRAS CIVIS* | [OBR 1] Execução das obras civis - PRÉDIO ANEXO | [OBR 1] Execução das obras civis - PRÉDIO ANEXO |  | Valeria Ferro |  | A Iniciar | 2027-03-01 | 2028-03-01 | 366
PROJETOS | OBRAS CIVIS* | [OBR 1] Execução das obras civis - PRÉDIO ANEXO |  |  | Valeria Ferro |  | A Iniciar
CONTEÚDO | CONTEÚDO |  | CONTEÚDO |  |  |  | A Iniciar
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL |  | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-08-01 | 2028-10-31 | 822
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [MUS 1] Aprofundamento do plano museológico | [MUS 1] Aprofundamento do plano museológico |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-07-01 | 2028-10-31 | 488
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [MUS 1] Aprofundamento do plano museológico | Revisão e detalhamento do programa de necessidades museológicas |  | Amarílis Lage de Macedo |  | A Iniciar | 2028-01-01 | 2028-03-31 | 90
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [MUS 1] Aprofundamento do plano museológico | Definição da política de acervos, pesquisa e documentação |  | Amarílis Lage de Macedo |  | A Iniciar | 2028-01-01 | 2028-08-31 | 243
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [MUS 1] Aprofundamento do plano museológico | Plano de educação e ação cultural |  | Amarílis Lage de Macedo |  | A Iniciar | 2028-03-01 | 2028-10-31 | 244
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [MUS 1] Aprofundamento do plano museológico | Plano de comunicação e identidade visual do plano museológico |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-07-01 | 2027-12-31 | 183
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [MUS 1] Aprofundamento do plano museológico | Entrega do plano museológico consolidado |  | Amarílis Lage de Macedo |  | A Iniciar | 2028-01-01 | 2028-10-31 | 304
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [CUR 1] Revisão e detalhamento do projeto curatorial | [CUR 1] Revisão e detalhamento do projeto curatorial |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-08-01 | 2027-07-31 | 364
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [CUR 1] Revisão e detalhamento do projeto curatorial | Revisão das mensagens central e secundárias à luz dos espaços definitivos |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-08-01 | 2026-10-31 | 91
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [CUR 1] Revisão e detalhamento do projeto curatorial | Detalhamento da narrativa por área (11 áreas + arena externa) |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-09-01 | 2027-01-31 | 152
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [CUR 1] Revisão e detalhamento do projeto curatorial | Definição de referências visuais e objetos de acervo por área |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-02-28 | 150
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [CUR 1] Revisão e detalhamento do projeto curatorial | Workshop de alinhamento com equipe de expografia |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-01-01 | 2027-03-31 | 89
CONTEÚDO | CONTEÚDO: PLANO MUSEOLÓGICO E PROJETO CURATORIAL | [CUR 1] Revisão e detalhamento do projeto curatorial | Entrega do texto curatorial consolidado |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-06-01 | 2027-07-31 | 60
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS |  | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS |  |  |  | A Iniciar | 2026-10-01 | 2027-12-31 | 456
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | [CON 1] Desenvolvimento de conteúdos para a ELD |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-12-31 | 456
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 1: O Sol (fonte primordial) |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-03-31 | 181
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Comissionamento e desenvolvimento da instalação sensorial (Área 1 — O Sol / grande globo) |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-08-31 | 334
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 2: Energia e imaginação |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-03-31 | 181
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Comissionamento e desenvolvimento da grande escultura cinética (Área 2 — Salão Monumental) |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-08-31 | 334
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 3: O automóvel e o Brasil |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-03-31 | 181
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Edital e seleção de artista para obra da 'Chapel' (Área 4) — arte contemporânea |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-01-31 | 122
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 5: A potência do corpo |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-03-31 | 181
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 6: As eras energéticas |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-11-01 | 2027-04-30 | 180
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 7: Matriz brasileira |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-11-01 | 2027-04-30 | 180
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 8: Mergulho inovador (petróleo offshore) |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-11-01 | 2027-05-31 | 211
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 9: Grandes engrenagens |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-12-01 | 2027-05-31 | 181
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 10: Tendências para o futuro |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-12-01 | 2027-06-30 | 211
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Área 11: Do potencial à ação |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-01-01 | 2027-06-30 | 180
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Pesquisa e desenvolvimento de textos — Arena externa (Gasômetro) |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-01-01 | 2027-06-30 | 180
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Desenvolvimento de conteúdo audiovisual (filmes, animações, podcasts) |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-04-01 | 2027-12-31 | 274
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Desenvolvimento de conteúdo para experiências interativas digitais |  | Amarílis Lage de Macedo |  | A Iniciar | 2027-04-01 | 2027-12-31 | 274
CONTEÚDO | DESENVOLVIMENTO DE CONTEÚDOS E OBRAS COMISSIONADAS | [CON 1] Desenvolvimento de conteúdos para a ELD | Seleção e pesquisa de acervos e objetos físicos para a exposição |  | Amarílis Lage de Macedo |  | A Iniciar | 2026-10-01 | 2027-09-30 | 364
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA |  | EXPOGRAFIA E CENOGRAFIA |  |  |  | A Iniciar
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA |  | EXPOGRAFIA E CENOGRAFIA |  | Vitor Garcez de Oliveira |  | A Iniciar | 2026-10-01 | 2028-09-30 | 730
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | [EXP 1] Revisão e detalhamento do projeto de expografia |  | Vitor Garcez de Oliveira |  | A Iniciar | 2026-10-01 | 2027-09-30 | 364
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | Alinhamento com curadoria e revisão das premissas expográficas |  | Vitor Garcez de Oliveira |  | A Iniciar | 2026-10-01 | 2026-12-31 | 91
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | Estudo preliminar de expografia por área (11 áreas + arena) |  | Vitor Garcez de Oliveira |  | A Iniciar | 2026-11-01 | 2027-02-28 | 119
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | Projeto básico de expografia — circulação, volumetria, materiais |  | Vitor Garcez de Oliveira |  | A Iniciar | 2027-01-01 | 2027-04-30 | 119
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | Desenvolvimento de especificações técnicas para tecnologias e experiências interativas |  | Vitor Garcez de Oliveira |  | A Iniciar | 2027-03-01 | 2027-06-30 | 121
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | Projeto executivo de expografia (detalhamento completo) |  | Vitor Garcez de Oliveira |  | A Iniciar | 2027-05-01 | 2027-09-30 | 152
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 1] Revisão e detalhamento do projeto de expografia | Aprovação do projeto de expografia com curadoria e gestão |  | Vitor Garcez de Oliveira |  | A Iniciar | 2027-08-01 | 2027-09-30 | 60
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | [EXP 2] Execução da cenografia |  | Vitor Garcez de Oliveira |  | A Iniciar | 2027-10-01 | 2028-09-30 | 365
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | Contratação da(s) empresa(s) de cenografia e montagem |  | Vitor Garcez de Oliveira |  | A Iniciar | 2027-10-01 | 2027-12-01 | 61
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | Fabricação e pré-montagem de estruturas e mobiliário expográfico |  | Vitor Garcez de Oliveira |  | A Iniciar | 2028-01-01 | 2028-03-01 | 60
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | Montagem das estruturas no espaço do museu |  | Vitor Garcez de Oliveira |  | A Iniciar | 2028-03-01 | 2028-06-30 | 121
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | Instalação de sistemas audiovisuais, interativos e de iluminação expográfica |  | Vitor Garcez de Oliveira |  | A Iniciar | 2028-06-01 | 2028-07-31 | 60
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | Instalação e integração das obras comissionadas |  | Vitor Garcez de Oliveira |  | A Iniciar | 2028-06-01 | 2028-07-31 | 60
EXPOGRAFIA E CENOGRAFIA | EXPOGRAFIA E CENOGRAFIA | [EXP 2] Execução da cenografia | Colocação de textos, totens e elementos gráficos |  | Vitor Garcez de Oliveira |  | A Iniciar | 2028-08-31 | 2028-09-30 | 30
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU |  | GESTÃO E OPERAÇÃO DO MUSEU |  | Tatiana Paulino de Azevedo |  | A Iniciar
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU |  | GESTÃO E OPERAÇÃO DO MUSEU |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-06-01 | 2028-12-31 | 579
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 1] Seleção da OS gestora | [GES 1] Seleção da OS gestora |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-06-01 | 2027-11-30 | 182
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 1] Seleção da OS gestora | Lançamento do edital para operação do museu |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-06-01 | 2027-06-30 | 29
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 1] Seleção da OS gestora | Formação do Comitê Executivo do museu |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-07-01 | 2027-07-31 | 30
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 1] Seleção da OS gestora | Processo de seleção da OS gestora (análise de propostas, negociação) |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-08-01 | 2027-10-31 | 91
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 1] Seleção da OS gestora | Início do trabalho da OS responsável pela operação |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-11-01 | 2027-11-30 | 29
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 2] Implantação do modelo de gestão | [GES 2] Implantação do modelo de gestão |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-11-01 | 2028-12-31 | 426
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 2] Implantação do modelo de gestão | Inscrição do plano anual pela OS gestora |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2028-01-01 | 2028-01-31 | 30
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 2] Implantação do modelo de gestão | Contratação e formação da equipe operacional do museu |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2027-11-01 | 2028-06-30 | 242
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 2] Implantação do modelo de gestão | Desenvolvimento do programa de visitas mediadas e educativo |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2028-03-01 | 2028-09-30 | 213
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 2] Implantação do modelo de gestão | Implementação inicial do plano de gestão |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2028-11-01 | 2028-12-31 | 60
GESTÃO E OPERAÇÃO DO MUSEU | GESTÃO E OPERAÇÃO DO MUSEU | [GES 2] Implantação do modelo de gestão | Planejamento da programação inaugural e comunicação de abertura |  | Tatiana Paulino de Azevedo |  | A Iniciar | 2028-07-01 | 2028-10-31 | 122
COMUNICAÇÃO | COMUNICAÇÃO |  | COMUNICAÇÃO |  | Camila da Silva Costa |  | A Iniciar
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA |  | TESTES, COMISSIONAMENTO E ABERTURA |  | Camila da Silva Costa |  | A Iniciar | 2028-09-01 | 2028-12-31 | 121
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [TES 1] Testes e comissionamento | [TES 1] Testes e comissionamento |  | Camila da Silva Costa |  | A Iniciar | 2028-09-01 | 2028-10-31 | 60
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [TES 1] Testes e comissionamento | Testes técnicos de todos os sistemas (AV, interativos, iluminação, HVAC) |  | Camila da Silva Costa |  | A Iniciar | 2028-09-01 | 2028-09-30 | 29
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [TES 1] Testes e comissionamento | Visitações-teste com grupos de público (pré-abertura controlada) |  | Camila da Silva Costa |  | A Iniciar | 2028-10-01 | 2028-10-31 | 30
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [TES 1] Testes e comissionamento | Ajustes e correções finais — conteúdo, cenografia e sistemas |  | Camila da Silva Costa |  | A Iniciar | 2028-10-01 | 2028-10-31 | 30
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [ABR 1] Abertura do MUP — Nov/2028 ★ | [ABR 1] Abertura do MUP — Nov/2028 ★ |  | Camila da Silva Costa |  | A Iniciar | 2028-11-01 | 2028-11-30 | 29
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [ABR 1] Abertura do MUP — Nov/2028 ★ | Evento de abertura oficial para convidados e imprensa |  | Camila da Silva Costa |  | A Iniciar | 2028-11-01 | 2028-11-15 | 14
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [ABR 1] Abertura do MUP — Nov/2028 ★ | Abertura ao público geral |  | Camila da Silva Costa |  | A Iniciar | 2028-11-15 | 2028-11-30 | 15
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | [ABR 1] Abertura do MUP — Nov/2028 ★ | Monitoramento inicial e relatório de abertura |  | Camila da Silva Costa |  | A Iniciar | 2028-11-15 | 2028-12-31 | 46
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | Branding | Branding |  | Iago Gonçalves Pereira |  | Em Andamento
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | Branding | Aprovação interna naming |  | Iago Gonçalves Pereira |  | Em Andamento | 2026-07-01 | 2026-07-31 | 30
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | Branding | Aprovação em comitê naming |  | Iago Gonçalves Pereira |  | A Iniciar
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | Branding | Aprovação interna de identidade visual |  | Iago Gonçalves Pereira |  | Em Andamento | 2026-07-01 | 2026-07-31 | 30
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | Branding | Aprovação em comitê de identidade visual |  | Iago Gonçalves Pereira |  | A Iniciar
COMUNICAÇÃO | TESTES, COMISSIONAMENTO E ABERTURA | Branding | Elaboração de plano de comunicação pré abertura |  | Iago Gonçalves Pereira |  | A Iniciar
Formulas:
DATA INÍCIO = MIN([DATA INÍCIO, row below]:J300)
DATA FIM = MAX([DATA FIM, row below]:K300)
DATA FIM = [DATA INÍCIO]+[DURAÇÃO]
DURAÇÃO = DATEDIF([DATA INÍCIO],[DATA FIM],"d")

## longa por área (hidden)
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! |  |  | #REF! | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FOYER
#REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Página8 (hidden)
Eixo | Grupo | Marco / Entrega | Tarefa | Fornecedor | Responsável | Status | Data Início | Data Fim | Duração (dias)
FOYER
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ PISO | DEMOLIR PISO EXISTENTE EM GRANILITE MONOLÍTICO VERMELHO | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-05-01 | 30
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Dimensionar quantitativo |  | jadejares@gmail.com | Feito | 2026-04-20 | 2026-04-25 | 5
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Orçamento |  | Gabriela Carvalho | Feito | 2026-04-25 | 2026-04-30 | 5
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Contratação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-04-30 | 2026-05-20 | 20
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ PISO | ASSENTAR PISOS CIMENTÍCIOS FEITOS SOB ENCOMENDA, TIPO GRANILITE, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-01 | 2026-05-16 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequaçõesprojeto de incêdio | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Extração do material |  | Gabriela Carvalho | A iniciar | 2026-05-20 | 2026-05-30 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Logística de envio e recebimento |  | jadejares@gmail.com | A iniciar | 2026-05-30 | 2026-06-09 | 10
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | GUARDA CORPO MEZANINO FOYER: GUARDA CORPO EM VIDRO LAMINADO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURAS DE PAREDES E TETO EM DRYWALL, EXISTENTES NO FOYER EM TINTAS DE TERRA, COR: BARRO VERMELHO, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-09 | 2026-06-24 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | RECEBIMENTO DA TERRA DO MARAJÓ PARA PREPARO DE TINTA | MÃOS CARUANAS | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-06-09 | 0
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
ÁREA 0 (pinguela)
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-20 | 2026-07-04 | 45
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-20 | 2026-06-19 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-04-30 | 2026-05-30 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-06-03 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-03 | 2026-06-06 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Cotação e contratação | CLÉCIO | Gabriela Carvalho | Atrasado | 2026-02-08 | 2026-05-19 | 100
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Produção do material | CLÉCIO | Gabriela Carvalho | A iniciar | 2026-05-19 | 2026-06-08 | 20
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Prospecção do fornecedor | CLÉCIO | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-02-07 | 4
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Prototipagem do material | CLÉCIO | Tatiane Baptista Proba Rocha | Feito | 2026-01-20 | 2026-01-30 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Cabeamento de lógica e AV |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Chegada e preparo de cabos de rede e dados |  | Racquel Gabriele Prudente e Silva | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-07-14 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Logística e recebimento de equipamentos de som, imagem e rede |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-14 | 2026-06-28 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Instalação |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-03 | 2026-07-23 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Logística e recebimento de equipamentos e materiais |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-20 | 2026-07-04 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ARCONDICIONADO E DESUMIDIFICAÇÃO | Desmontagem de dutos e de máquinas que atrapalham a montagem | ICETECH | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-15 | 2026-05-18 | 3
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ARCONDICIONADO E DESUMIDIFICAÇÃO | Instalação | ICETECH | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-17 | 2026-07-02 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ARCONDICIONADO E DESUMIDIFICAÇÃO | Logística e recebimento de equipamentos | ICETECH | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-02 | 2026-06-17 | 15
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Ajustes e entrega final |  | Amarílis Lage de Macedo | A iniciar | 2026-07-01 | 2026-07-08 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Instalação do conteúdo |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-29 | 2026-07-01 | 2
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Testes e acabamentos |  | Amarílis Lage de Macedo | A iniciar | 2026-07-01 | 2026-07-06 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO DE MADEIRA MACIÇA PARA PISOS E CHAPINS | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-06-15 | 2026-06-30 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | FECHAMENTO PAREDES CURVAS ENTRE ÁREA 0 (CORREDOR) E 4-5: FECHAMENTOS DE PAREDES EM SISTEMA SANDUICHE COMPOSTO POR: FACES INTERNA E EXTERNA DA SALA EM COMPENSADO LAMINADO FLEXÍVEL IMUNIZADO E IGNIFUGADO (APLICADO EM 2 CAMADAS DE 6mm EM PAINÉIS DE 2500X1600) APARAFUSADO SOBRE SUBESTRUTURA EM SISTEMA DE STEELFRAME, APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO PARA VEDAÇÃO DO SISTEMA; MIOLO COM PREENCHIMENTO EM LÃ DE PET DENSIDADE MÍNIMA DE 15KG/M³ (CONFORME PROJETO DE ACÚSTICA). APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO DAS JUNTAS NA FACE INTERNA. FACE VOLTADA PARA ÁREA 0 (CORREDOR) SEM ACABAMENTO E FACE VOLTADA PARA SALAS 4 E 5 COM EMASSAMENTO COMPLETO E PINTURA ACRÍLICA EM COR A DEFINIR. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Locação - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-18 | 2026-05-18 | 0
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | PINGUELA E DIVERSIDADE EM PISO EXECUTADO EM SISTEMA ELEVADO COM ESTRUTURA EM BASE DE ALVENARIA E FECHAMENTO EM PISO WALL, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de sistema construtivo, agora o piso elevado será estruturado em alvenaria e placas de pisowall. | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-20 | 2026-07-05 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Recebimento de gabarito 1:1 - PINGUELA, DIVERSIDADE - lateral faixada | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-15 | 2026-05-15 | 0
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Validação arquitetura - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-19 | 2026-05-20 | 1
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | execução da alvenaria + revestimento de argamassa - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-21 | 2026-06-05 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | execução de Eletrica + Logica PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-05 | 2026-06-20 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Instalação da Assoalho do piso da pinguela | RCM | jadejares@gmail.com | Risco de atraso | 2026-07-05 | 2026-07-15 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Logística de chegada da madeira | RCM | Gabriela Carvalho | Feito | 2026-04-27 | 2026-05-04 | 7
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO "ÁGUA" DA PINGUELA | Instalação | CAMUFLAGEM | jadejares@gmail.com | A iniciar | 2026-06-15 | 2026-06-20 | 5
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO "ÁGUA" DA PINGUELA | Recebimento do material | INTERNO | jadejares@gmail.com | A iniciar | 2026-06-08 | 2026-06-15 | 7
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA DE TABOA | Instalação do material | CAMUFLAGEM | jadejares@gmail.com | A iniciar | 2026-05-24 | 2026-06-13 | 20
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA DE TABOA | Logística da Taboa | INTERNO | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-17 | 2026-05-22 | 5
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA DE TABOA | Recortes na Taboa com artesões da Trapos e Fiapos | TRAPOS E FIAPOS | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-08 | 2026-06-13 | 5
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA FACHADA | Instalação do Material | CAMUFLAGEM | jadejares@gmail.com | A iniciar | 2026-05-31 | 2026-06-20 | 20
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA FACHADA | Logística | INTERNO | jadejares@gmail.com | Definir datas | 2026-05-27 | 2026-05-31 | 4
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de detalhamento para conteúdo | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-30 | 2026-05-15 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
ÁREA 1 (diversidade)
|  |  | Compra da réplica |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-05-15 | 2026-05-30 | 15
|  |  | Molde |  | Débora Pires da Silva Rodrigues | Feito | 2026-05-07 | 2026-05-15 | 8
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-20 | 2026-07-04 | 45
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-20 | 2026-06-19 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-04-30 | 2026-05-30 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-06-03 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-03 | 2026-06-06 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BICHOS DE MIRITI | Cotação e contratação | SEU VALDELI | Débora Pires da Silva Rodrigues | Feito | 2025-12-02 | 2025-12-26 | 24
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BICHOS DE MIRITI | Logística e entrega no museu | SEU VALDELI | Débora Pires da Silva Rodrigues | Risco de atraso | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BICHOS DE MIRITI | Produção do material | SEU VALDELI | Tatiane Baptista Proba Rocha | Em andamento | 2026-02-03 | 2026-05-14 | 100
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Cotação e contratação | CLÉCIO | Gabriela Carvalho | Atrasado | 2026-02-08 | 2026-05-19 | 100
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Produção do material | CLÉCIO | Gabriela Carvalho | A iniciar | 2026-05-19 | 2026-06-08 | 20
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Prospecção do fornecedor | CLÉCIO | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-02-07 | 4
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | ÁGUA DA PINGUELA | Prototipagem do material | CLÉCIO | Tatiane Baptista Proba Rocha | Feito | 2026-01-20 | 2026-01-30 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Cabeamento de lógica e AV |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Chegada e preparo de cabos de rede e dados |  | Racquel Gabriele Prudente e Silva | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-07-14 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Logística e recebimento de equipamentos de som, imagem e rede |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-14 | 2026-06-28 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Instalação |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-03 | 2026-07-23 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Logística e recebimento de equipamentos e materiais |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-20 | 2026-07-04 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 1 ¦ DIVERSIDADE | Testes e ajustes de conteúdo | Roberta Carvalho | Vitor Garcez de Oliveira | A iniciar | 2026-07-01 | 2026-07-10 | 9
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 1 ¦ DIVERSIDADE | Versão Final do filme da Roberta Carvalho | Roberta Carvalho | Vitor Garcez de Oliveira | A iniciar | 2026-06-25 | 2026-06-26 | 1
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 1 ¦ DIVERSIDADE | Video mapping | Inovatec | Vitor Garcez de Oliveira | A iniciar | 2026-06-26 | 2026-07-01 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | MÓBILE DE MIRITI | Instalação |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-06-19 | 2026-07-29 | 40
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | MÓBILE DE MIRITI | Recebimento do material |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-05-19 | 2026-05-22 | 3
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | VITRINES DE INSETOS | Chegada dos insetos no museu |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-06-17 | 2026-06-20 | 3
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | VITRINES DE INSETOS | Laudos de museologia |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-06-20 | 2026-06-25 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | VITRINES DE INSETOS | montagem das vitrines |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-06-25 | 2026-07-05 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | VITRINES LÍTICOS E OSSOS | Chegada dos líticos no museu |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-05-25 | 2026-05-25 | 0
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | VITRINES LÍTICOS E OSSOS | Laudos de museologia |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-05-25 | 2026-05-30 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | VITRINES LÍTICOS E OSSOS | montagem das vitrines |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-06-27 | 2026-07-07 | 10
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO DE MADEIRA MACIÇA PARA PISOS E CHAPINS | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-06-15 | 2026-06-30 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | FECHAMENTO PAREDES CURVAS ENTRE ÁREA 0 (CORREDOR) E 4-5: FECHAMENTOS DE PAREDES EM SISTEMA SANDUICHE COMPOSTO POR: FACES INTERNA E EXTERNA DA SALA EM COMPENSADO LAMINADO FLEXÍVEL IMUNIZADO E IGNIFUGADO (APLICADO EM 2 CAMADAS DE 6mm EM PAINÉIS DE 2500X1600) APARAFUSADO SOBRE SUBESTRUTURA EM SISTEMA DE STEELFRAME, APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO PARA VEDAÇÃO DO SISTEMA; MIOLO COM PREENCHIMENTO EM LÃ DE PET DENSIDADE MÍNIMA DE 15KG/M³ (CONFORME PROJETO DE ACÚSTICA). APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO DAS JUNTAS NA FACE INTERNA. FACE VOLTADA PARA ÁREA 0 (CORREDOR) SEM ACABAMENTO E FACE VOLTADA PARA SALAS 4 E 5 COM EMASSAMENTO COMPLETO E PINTURA ACRÍLICA EM COR A DEFINIR. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Instalação da ESPIRAL DIVERSIDADE ESTRUTURADAS POR TUBOS METÁLICOS FIXADOS NA ESTRUTURA PRINCIPAL DAS PAREDES E SUSPENSOS NA ESTRUTURA METÁLICA EXISTENTE DO GALPÃO. CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica e simplificação da volumetria; teto deixa de ser inclinado e será construído totalmente plano. Revisões foram consideradas para simplifcar execução e montagem. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-06-19 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | PINTURA da ESPIRAL DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-19 | 2026-06-24 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | DIVERSIDADE PAREDES CURVAS E ESPIRAL: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica, simplificação de perfis e volumetria. Revisões foram consideradas para simplifcar execução e montagem. | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-09 | 2026-06-19 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | PINTURA DIVERSIDADE PAREDES CURVAS E ESPIRAL | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-19 | 2026-06-24 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Locação - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-18 | 2026-05-18 | 0
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | PINGUELA E DIVERSIDADE EM PISO EXECUTADO EM SISTEMA ELEVADO COM ESTRUTURA EM BASE DE ALVENARIA E FECHAMENTO EM PISO WALL, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de sistema construtivo, agora o piso elevado será estruturado em alvenaria e placas de pisowall. | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-20 | 2026-07-05 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Recebimento de gabarito 1:1 - PINGUELA, DIVERSIDADE - lateral faixada | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-15 | 2026-05-15 | 0
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Validação arquitetura - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-19 | 2026-05-20 | 1
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | execução da alvenaria + revestimento de argamassa - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-21 | 2026-06-05 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | execução de Eletrica + Logica PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-05 | 2026-06-20 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PAREDES | DIVERSIDADE: sanduíche de madeira com material acústico no meio | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-19 | 2026-06-29 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Instalação da Assoalho do piso da pinguela | RCM | jadejares@gmail.com | Risco de atraso | 2026-07-05 | 2026-07-15 | 10
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA DE TABOA | Instalação do material | CAMUFLAGEM | jadejares@gmail.com | A iniciar | 2026-05-24 | 2026-06-13 | 20
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA DE TABOA | Logística da Taboa | INTERNO | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-17 | 2026-05-22 | 5
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA DE TABOA | Recortes na Taboa com artesões da Trapos e Fiapos | TRAPOS E FIAPOS | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-08 | 2026-06-13 | 5
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA FACHADA | Instalação do Material | CAMUFLAGEM | jadejares@gmail.com | A iniciar | 2026-05-31 | 2026-06-20 | 20
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CORTINA FACHADA | Logística | INTERNO | jadejares@gmail.com | Definir datas | 2026-05-27 | 2026-05-31 | 4
PRODUÇÃO DE CONTEÚDO | OBJETOS | DENTES DE PURUSSAURUS E JACARÉ | Confecção das réplicas |  | Laura de Paula Rago | Feito | 2026-04-12 | 2026-05-22 | 40
PRODUÇÃO DE CONTEÚDO | OBJETOS | DENTES DE PURUSSAURUS E JACARÉ | Documentação dos objetos |  | Gabriele de Oliveira Martins | A iniciar | 2026-06-11 | 2026-06-21 | 10
PRODUÇÃO DE CONTEÚDO | OBJETOS | DENTES DE PURUSSAURUS E JACARÉ | Pesquisa de objetos originais para fazer molde |  | Laura de Paula Rago | Feito | 2026-01-01 | 2026-04-01 | 90
PRODUÇÃO DE CONTEÚDO | OBJETOS | DENTES DE PURUSSAURUS E JACARÉ | Transporte dos objetos para o Museu |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-05-30 | 2026-06-11 | 12
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Apresentação do primeiro corte (v1) | ROBERTA CARVALHO | Vitor Garcez de Oliveira | Em andamento | 2026-04-08 | 2026-05-20 | 42
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Apresentação do segundo corte (v2) | ROBERTA CARVALHO | Vitor Garcez de Oliveira | A iniciar | 2026-05-25 | 2026-06-15 | 21
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Contratação | ROBERTA CARVALHO | Débora Pires da Silva Rodrigues | Feito | 2026-01-16 | 2026-01-16 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Entrega de storyboard cena a cena | ROBERTA CARVALHO | Vitor Garcez de Oliveira | Feito | 2026-03-05 | 2026-03-18 | 13
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Envio da ficha-base com pesquisa + direcionamentos compilados | ROBERTA CARVALHO | Laura de Paula Rago | Feito | 2026-01-21 | 2026-01-21 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Envio de pré-roteiro pela equipe de conteúdo IDG | ROBERTA CARVALHO | Amarílis Lage de Macedo | Feito | 2026-01-23 | 2026-01-23 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Envio do Roteiro Preliminar de Atmosfera para Roberta | ROBERTA CARVALHO | Laura de Paula Rago | Feito | 2025-12-08 | 2025-12-11 | 3
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Primeira apresentação de roteiro pela Roberta | ROBERTA CARVALHO | Vitor Garcez de Oliveira | Feito | 2026-02-04 | 2026-02-27 | 23
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Reorganização de Fluxo | ROBERTA CARVALHO | Laura de Paula Rago | Feito | 2026-01-12 | 2026-01-14 | 2
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Revisão e Feedback do stryboard | ROBERTA CARVALHO | Vitor Garcez de Oliveira | Feito | 2026-03-18 | 2026-04-02 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Revisão e Feedback primeiro corte (v1) | ROBERTA CARVALHO | Vitor Garcez de Oliveira | A iniciar | 2026-05-20 | 2026-05-25 | 5
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 1 ¦ DIVERSIDADE | Revisão e Feedback segundo corte (v2) | ROBERTA CARVALHO | Vitor Garcez de Oliveira | A iniciar | 2026-06-15 | 2026-06-25 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Apresentação versão revisada mapas (POLES+Suplab) | GABRIEL KOSLOVSKI | Vitor Garcez de Oliveira | Feito | 2026-03-09 | 2026-04-08 | 30
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Contratação Gabriel Koslowski | GABRIEL KOSLOVSKI | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Contratação SUPLAB | GABRIEL KOSLOVSKI | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Definição de dispositivo tecnologia | GABRIEL KOSLOVSKI | Vitor Garcez de Oliveira | Feito | 2026-01-05 | 2026-03-09 | 63
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Envio de imagens | GABRIEL KOSLOVSKI | Amarílis Lage de Macedo | Atrasado | 2026-04-08 | 2026-05-08 | 30
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Feedback curadoria | GABRIEL KOSLOVSKI | Vitor Garcez de Oliveira | Feito | 2026-04-08 | 2026-04-15 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Feedback curadoria | GABRIEL KOSLOVSKI | Amarílis Lage de Macedo | Risco de atraso | 2026-05-14 | 2026-05-20 | 6
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Contratação | COLETIVO SHIPIBO | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Cotar e contratar a captação de áudio e do Canto em Belém | COLETIVO SHIPIBO | Débora Pires da Silva Rodrigues | Em andamento | 2026-04-20 | 2026-05-31 | 41
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Cotação e compra de materiais para a pintura | COLETIVO SHIPIBO | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-15 | 2026-06-15 | 31
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Cotação e contratação de logística viagem | COLETIVO SHIPIBO | Débora Pires da Silva Rodrigues | Em andamento | 2026-04-29 | 2026-05-29 | 30
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Definir o Suporte e a Técnica com Arquitetura | COLETIVO SHIPIBO | Vitor Garcez de Oliveira | Feito | 2026-02-27 | 2026-02-27 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Definição de próximas etapas | COLETIVO SHIPIBO | Laura de Paula Rago | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Entrega das referências | COLETIVO SHIPIBO | Laura de Paula Rago | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MURAL SHIPIBO | Feedback curadoria | COLETIVO SHIPIBO | Laura de Paula Rago | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Briefing e contratação Iza Lessa | IZA LESSA | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-07 | 2026-05-30 | 23
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Definição de equipamentos e lista de equipamentos a serem comprados | IZA LESSA | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-15 | 2026-05-22 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Desenvolvimento da experiência e design | IZA LESSA | Amarílis Lage de Macedo | Em andamento | 2026-05-15 | 2026-06-29 | 45
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Plano de trabalho com a artista | IZA LESSA | Débora Pires da Silva Rodrigues | Feito | 2026-05-14 | 2026-05-30 | 16
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA X ¦ MESA DAS INTERAÇÕES DAS ESPÉCIES | Testes e aprovações | IZA LESSA | Amarílis Lage de Macedo | A iniciar | 2026-06-29 | 2026-07-14 | 15
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Revisão |  | Amarílis Lage de Macedo | A iniciar | 2026-05-17 | 2026-05-27 | 10
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Tradução |  | Amarílis Lage de Macedo | A iniciar | 2026-05-27 | 2026-06-03 | 7
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Anteprojeto básico parcial (áreas 1,2 e 3) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-10-07 | 2025-10-31 | 24
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de detalhamento para conteúdo | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-30 | 2026-05-15 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
PROJETOS COMPLEMENTARES | TECNOLOGIA E AUDIOVISUAL |  | Revisão da Diversidade | INOVATEC | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-02 | 50
ÁREA 2 (oralidade e tecnologias)
|  |  | Desenvolvimento preliminar do videomapping (conteúdo) | GABRIELA BILÁ | Vitor Garcez de Oliveira | Definir datas
|  |  | Finalização do videommaping | GABRIELA BILÁ | Vitor Garcez de Oliveira | Definir datas
|  |  | Validação do videomapping pela curadoria | GABRIELA BILÁ | Vitor Garcez de Oliveira | Definir datas
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-20 | 2026-07-04 | 45
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-20 | 2026-06-19 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-04-30 | 2026-05-30 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-06-03 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-03 | 2026-06-06 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Cabeamento de lógica e AV |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Chegada e preparo de cabos de rede e dados |  | Racquel Gabriele Prudente e Silva | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-07-14 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Logística e recebimento de equipamentos de som, imagem e rede |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-14 | 2026-06-28 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Instalação |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-03 | 2026-07-23 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Logística e recebimento de equipamentos e materiais |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-20 | 2026-07-04 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ARCONDICIONADO E DESUMIDIFICAÇÃO | Desmontagem de dutos e de máquinas que atrapalham a montagem | ICETECH | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-15 | 2026-05-18 | 3
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ARCONDICIONADO E DESUMIDIFICAÇÃO | Instalação | ICETECH | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-17 | 2026-07-02 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ARCONDICIONADO E DESUMIDIFICAÇÃO | Logística e recebimento de equipamentos | ICETECH | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-02 | 2026-06-17 | 15
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ MAPAS | Ajustes e entrega final |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-24 | 2026-07-04 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ MAPAS | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-19 | 2026-06-24 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ MESA TECNOLOGIAS INTEGRADAS | Instalação da obra/maquete no local |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-11 | 2026-06-14 | 3
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ MESA TECNOLOGIAS INTEGRADAS | Logística |  | Wellington Bruno Soares da Silva | A iniciar | 2026-06-06 | 2026-06-11 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ MESA TECNOLOGIAS INTEGRADAS | Testes preliminares e ajustes |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-14 | 2026-06-24 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Ajustes e entrega final |  | Laura de Paula Rago | A iniciar | 2026-06-25 | 2026-06-30 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Inclusão de conteúdo (áudios) nas instalações da sala |  | Laura de Paula Rago | A iniciar | 2026-06-19 | 2026-06-20 | 1
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Instalação da parte física no museu |  | Laura de Paula Rago | A iniciar | 2026-06-16 | 2026-06-19 | 3
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Testes de conteúdo e da interação física |  | Laura de Paula Rago | A iniciar | 2026-06-20 | 2026-06-25 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Transporte do ventilador de São Paulo para Belém |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-09 | 2026-06-16 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ÁREA 2 ¦ MURAL SHIPIBO | Execução da pintura |  | Laura de Paula Rago | A iniciar | 2026-07-01 | 2026-07-08 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ÁREA 2 ¦ MURAL SHIPIBO | Gravação da execução da obra |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-07-01 | 2026-07-08 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ÁREA 2 ¦ MURAL SHIPIBO | Logística de viagem das artistas |  | Débora Pires da Silva Rodrigues | Em andamento | 2026-04-02 | 2026-05-30 | 58
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ÁREA 2 ¦ SALA ORALIDADE ¦ PAINEL MARAJOARA | Embalagem e transporte das peças |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-02 | 2026-06-10 | 8
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ÁREA 2 ¦ SALA ORALIDADE ¦ PAINEL MARAJOARA | Instalação da obra no Museu | RONALDO GUEDES | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-16 | 2026-06-23 | 7
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO DE MADEIRA MACIÇA PARA PISOS E CHAPINS | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-06-15 | 2026-06-30 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | DEMOLIR FORRO EXISTENTE (GESSO ACARTONADO) ABAIXO DO MEZANINO PARA PASSAGEM DE INFRAESTRUTURAS ELÉTRICAS, DADOS E REFORÇOS ESTRUTURAIS, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | FORRO A CONSTRUIR (GESSO ACARTADONO) ABAIXO DO MEZANINO, COM ACABAMENTO EM PINTURA DE TERRA OU SIMILAR, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-31 | 2026-06-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | PAINEL DE VIDRO TERRA PRETA ÁREA 3: 2 FACES DE VIDRO EM VIDRO LAMINADO E ESTRUTURA EM AÇO INOX | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | SALA ORALIDADE – ÁREA 2: BANCO EM ALVENARIA CURVO COM EMBOÇO PREPARADO PARA APLICAÇÃO DE REVESTIMENTO MONOLÍTICO (CHUKUN OU SIMILAR) | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | ORALIDADE: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO ESTRUTURAL + FECHAMENTO EM CHAPAS DE COMPENSADO, NÚCLEO PREENCHIDO COM ISOLAMENTO ACÚSTICO A SER DEFINIDO. CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL Houve mudança de projeto considerando diminuição do peso da estrutura metálica. | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-05-15 | 44
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Locação - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-18 | 2026-05-18 | 0
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | PINGUELA E DIVERSIDADE EM PISO EXECUTADO EM SISTEMA ELEVADO COM ESTRUTURA EM BASE DE ALVENARIA E FECHAMENTO EM PISO WALL, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de sistema construtivo, agora o piso elevado será estruturado em alvenaria e placas de pisowall. | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-20 | 2026-07-05 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | PISO DA ORALIDADE EM SISTEMA ELEVADO COM ESTRUTURA EM BASE DE ALVENARIA E FECHAMENTO EM PISO WALL, CONFORME PROJETO EXPOGRÁFICO. Houve mudança de sistema construtivo, agora o piso elevado será estruturado em alvenaria e placas de pisowall. | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-07-05 | 2026-07-10 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Recebimento de gabarito 1:1 - PINGUELA, DIVERSIDADE - lateral faixada | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-15 | 2026-05-15 | 0
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Validação arquitetura - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-19 | 2026-05-20 | 1
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | execução da alvenaria + revestimento de argamassa - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-21 | 2026-06-05 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | execução de Eletrica + Logica PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-05 | 2026-06-20 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PAREDES | ORALIDADE: sanduíche de madeira com material acústico no meio | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-15 | 2026-05-25 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Instalação da Assoalho do piso da pinguela | RCM | jadejares@gmail.com | Risco de atraso | 2026-07-05 | 2026-07-15 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Instalação do piso da Oralidade | RCM | jadejares@gmail.com | A iniciar | 2026-07-15 | 2026-07-20 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Logística de chegada da madeira | RCM | Gabriela Carvalho | Feito | 2026-04-27 | 2026-05-04 | 7
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | REVESTIMENTOS | ORALIDADE: chukun ORALIDADE: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL INCLUINDO TRECHO DE PAREDE EM ALVENARIA PARA SUPORTE A PAINEL CERÂMICO. Houve mudança de projeto considerando diminuição do peso da estrutura metálica. | RCM | jadejares@gmail.com | Definir datas | 2026-05-25 | 2026-06-09 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Envio de imagens | GABRIEL KOSLOVSKI | Amarílis Lage de Macedo | Atrasado | 2026-04-08 | 2026-05-08 | 30
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ MAPAS | Feedback curadoria | GABRIEL KOSLOVSKI | Amarílis Lage de Macedo | Risco de atraso | 2026-05-14 | 2026-05-20 | 6
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ Mesa das tecnologias intregadas (Gabriela Bilá) | Contratação | GABRIELA BILÁ | Débora Pires da Silva Rodrigues | Feito | 2026-03-01 | 2026-03-13 | 12
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ Mesa das tecnologias intregadas (Gabriela Bilá) | Desenvolvimento conceitual e especificação de equipamentos | GABRIELA BILÁ | Vitor Garcez de Oliveira | Atrasado | 2026-03-13 | 2026-05-07 | 55
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ Mesa das tecnologias intregadas (Gabriela Bilá) | Detalhamento técnico da estrutura da mesa | GABRIELA BILÁ | Vitor Garcez de Oliveira | A iniciar | 2026-05-12 | 2026-05-22 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ Mesa das tecnologias intregadas (Gabriela Bilá) | Fabricação da mesa (Marcelo Vaz) | MARCELO VAZ | Vitor Garcez de Oliveira | A iniciar | 2026-05-22 | 2026-06-06 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ Mesa das tecnologias intregadas (Gabriela Bilá) | Pesquisa adicional (se necessário) | GABRIELA BILÁ | Amarílis Lage de Macedo | Em andamento | 2026-05-12 | 2026-05-27 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ Mesa das tecnologias intregadas (Gabriela Bilá) | Validação conceitual com curadoria | GABRIELA BILÁ | Vitor Garcez de Oliveira | Feito | 2026-05-07 | 2026-05-12 | 5
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Aluguel e compra de equipamentos e dispositivos para testes | LEANDRO LIMA | Débora Pires da Silva Rodrigues | Feito | 2026-04-13 | 2026-04-30 | 17
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Casting de personagens e envio para produção do Leandro Lima | LEANDRO LIMA | Laura de Paula Rago | Feito | 2026-03-11 | 2026-03-31 | 20
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Compra dos equipamentos finais | LEANDRO LIMA | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-08 | 2026-05-30 | 22
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Contratação Karla Martins | LEANDRO LIMA | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-03-06 | 35
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Contratação Leandro Lima | LEANDRO LIMA | Débora Pires da Silva Rodrigues | Feito | 2026-02-06 | 2026-03-13 | 35
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Definição das histórias e palavras a serem animadas e entrega do roteiro para locução - Helena e Erendira + Karla | LEANDRO LIMA | Amarílis Lage de Macedo | Feito | 2026-02-02 | 2026-03-11 | 37
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Desenvolvimento da animação (palavras) | LEANDRO LIMA | Laura de Paula Rago | Em andamento | 2026-04-30 | 2026-05-22 | 22
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Edição das histórias gravadas | LEANDRO LIMA | Laura de Paula Rago | Em andamento | 2026-05-08 | 2026-05-22 | 14
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Entrega da gravação | LEANDRO LIMA | Laura de Paula Rago | A iniciar | 2026-05-22 | 2026-05-29 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Gravação das histórias | LEANDRO LIMA | Laura de Paula Rago | Feito | 2026-04-20 | 2026-05-08 | 18
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Lista e Compra de equipamentos e dispositivos para testes | LEANDRO LIMA | Débora Pires da Silva Rodrigues | Feito | 2026-04-01 | 2026-04-10 | 9
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Revisão da edição histórias gravadas | LEANDRO LIMA | Laura de Paula Rago | A iniciar | 2026-05-29 | 2026-06-05 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Testes da experiência e da animação e aprovação | LEANDRO LIMA | Laura de Paula Rago | Atrasado | 2026-05-01 | 2026-05-15 | 14
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ EXPERIÊNCIA | Validação final de equipamentos e outros dispositivos da experiência | LEANDRO LIMA | Laura de Paula Rago | Feito | 2026-04-30 | 2026-05-08 | 8
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ PAINEL MARAJOARA | Confecção das peças que serão instaladas no museu | RONALDO GUEDES | Débora Pires da Silva Rodrigues | Em andamento | 2026-04-04 | 2026-06-02 | 59
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ PAINEL MARAJOARA | Contratação | RONALDO GUEDES | Débora Pires da Silva Rodrigues | Feito | 2026-02-01 | 2026-04-02 | 60
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 2 ¦ SALA ORALIDADE ¦ PAINEL MARAJOARA | Desenvolvimento da arte e aprovação das curadoras | RONALDO GUEDES | Laura de Paula Rago | Feito | 2026-03-02 | 2026-03-05 | 3
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Revisão |  | Amarílis Lage de Macedo | A iniciar | 2026-05-17 | 2026-05-27 | 10
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Tradução |  | Amarílis Lage de Macedo | A iniciar | 2026-05-27 | 2026-06-03 | 7
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Anteprojeto básico parcial (áreas 1,2 e 3) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-10-07 | 2025-10-31 | 24
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de detalhamento para conteúdo | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-30 | 2026-05-15 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
ÁREA 3 (aturá e feira)
|  |  | Chegada das compras | MARLUS | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-05 | 2026-06-14 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-20 | 2026-07-04 | 45
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-20 | 2026-06-19 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-04-30 | 2026-05-30 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-06-03 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-03 | 2026-06-06 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Cabeamento de lógica e AV |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Chegada e preparo de cabos de rede e dados |  | Racquel Gabriele Prudente e Silva | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-07-14 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Logística e recebimento de equipamentos de som, imagem e rede |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-14 | 2026-06-28 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Instalação |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-03 | 2026-07-23 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Logística e recebimento de equipamentos e materiais |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-20 | 2026-07-04 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 3 ¦ ATURÁ | Ajustes e entrega final |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-21 | 2026-06-26 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 3 ¦ ATURÁ | Inclusão de conteúdos da experiência (céu e pintura) |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-06-16 | 2
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 3 ¦ ATURÁ | Montagem da experiência no museu |  | Laura de Paula Rago | A iniciar | 2026-06-14 | 2026-06-21 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 3 ¦ ATURÁ | Testes de conteúdo e da interação física |  | Laura de Paula Rago | A iniciar | 2026-06-21 | 2026-06-26 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 3 ¦ ATURÁ | Transporte da engenharia mesa para Belém |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-04 | 2026-06-11 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | FOTOS FINE ART ¦ ÁREAS 3 E 4 | Frete |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-03 | 2026-07-10 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | FOTOS FINE ART ¦ ÁREAS 3 E 4 | Montagem |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-10 | 2026-07-15 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | FOTOS FINE ART ¦ ÁREAS 3 E 4 | Produção gráfica |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-03 | 2026-07-03 | 0
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | OBJETOS ATURÁ | Objetos de Franci Braniwa |  | Jomara Ferreira Chaves Santos | A iniciar | 2026-06-16 | 2026-06-19 | 3
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURA EM GUARDACORPO EM DRYWALL EXISTENTE, EM TODA VOLTA DO MEZANINO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-07-09 | 30
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | DEMOLIR FORRO EXISTENTE (GESSO ACARTONADO) ABAIXO DO MEZANINO PARA PASSAGEM DE INFRAESTRUTURAS ELÉTRICAS, DADOS E REFORÇOS ESTRUTURAIS, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | FORRO A CONSTRUIR (GESSO ACARTADONO) ABAIXO DO MEZANINO, COM ACABAMENTO EM PINTURA DE TERRA OU SIMILAR, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-31 | 2026-06-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | MARETÓRIO: PAINEL COMPOSTO DE GRADIL EM CHAPA EXPANDIDA COM MONTANTES METÁLICOS VERTICAIS FIXADOS NO PISO E NO TETO, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | SALA ATURÁ – ÁREA 3: FECHAMENTO DE PAREDES E TETO EM SISTEMA DRYWALL FLEXÍVEL (APLICADO EM 2 CAMADAS DE 6MM) E MIOLO COM PREENCHIMENTO EM LÃ DE PET DENSIDADE MÍNIMA DE 15KG/M³ (CONFORME PROJETO DE ACÚSTICA). APLICAÇÃO DE FITAS TELADAS NAS JUNTAS E MASSA ESPECÍFICA PARA USO EM DRYWALL. EMASSAMENTO COMPLETO DE PAREDES E PINTURA ACRÍLICA COR A DEFINIR. | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-07-15 | 2026-07-30 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | TOPO DO ATURÁ EM VIGAMENTO METÁLICO PARA ESTRUTURAR COBERTURA DO CONJUNTO, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica. | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-05-15 | 44
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | ATURÁ: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO ESTRUTURAL. VERIFICAR PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica. | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-05-15 | 44
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PAREDES | ATURÁ: sanduíche de madeira com material acústico no meio | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-15 | 2026-05-25 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | REVESTIMENTOS | ATURÁ: muxarabi ATURÁ: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL Houve mudança de projeto considerando diminuição do peso da estrutura metálica. | RCM | jadejares@gmail.com | A iniciar | 2026-05-25 | 2026-06-09 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Avaliação das imagens das constalações | MOLA | Laura de Paula Rago | Feito | 2026-04-06 | 2026-04-08 | 2
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Compra de material para desenvolvimento da mesa | MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-03-13 | 2026-05-05 | 53
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Contratação Consultoria Marlus | MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Contratação Frank | FRANK BANIWA | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Contratação desenvolvimento Marlus | MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-02-02 | 2026-03-19 | 45
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Definição da lista final de equipamentos | MARLUS | Vitor Garcez de Oliveira | Feito | 2026-03-01 | 2026-03-13 | 12
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Desenvolvimento Pintura pelo Frank | FRANK BANIWA | Laura de Paula Rago | Feito | 2026-02-27 | 2026-02-27 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Documentação museológica | FRANK BANIWA | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-16 | 2026-06-19 | 3
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Entrega da Consultoria do Marlus Realizada | MARLUS | Tatiane Baptista Proba Rocha | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Feedback do roteiro | CURADORAS | Laura de Paula Rago | Atrasado | 2026-05-11 | 2026-05-16 | 5
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Fotografar / digitalizar a obra do Frank | FRANK BANIWA | Débora Pires da Silva Rodrigues | Feito | 2026-03-06 | 2026-05-10 | 65
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Gravação de áudio dobre Calendário x Constelação | INTERNO | Laura de Paula Rago | A iniciar | 2026-05-16 | 2026-05-31 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Recebimento da pintura no idg | FRANK BANIWA | Débora Pires da Silva Rodrigues | Feito | 2026-02-27 | 2026-03-06 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Roteiro da Gravação Calendário x Constelação | INTERNO | Laura de Paula Rago | Atrasado | 2026-04-01 | 2026-05-11 | 40
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Transportar a obra para o Museu | FRANK BANIWA | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-09 | 2026-06-16 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 3 ¦ ATURÁ | Tratamento das imagens | MOLA | Laura de Paula Rago | Feito | 2026-04-08 | 2026-05-18 | 40
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Contratação/Comissionamento |  | Tamires de Figueiredo Pinheiro | Em andamento | 2026-02-23 | 2026-06-03 | 100
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Impressão de fotos |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-13 | 2026-07-03 | 20
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Moldura (definir) |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-03 | 2026-06-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Recebimento de fotos |  | Laura de Paula Rago | Feito | 2026-01-12 | 2026-01-29 | 17
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Recebimento de fotos em alta |  | Débora Pires da Silva Rodrigues | Risco de atraso | 2026-06-03 | 2026-06-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Seleção de artistas |  | Laura de Paula Rago | Feito | 2026-01-16 | 2026-01-16 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Seleção final de fotos |  | Laura de Paula Rago | Feito | 2026-01-28 | 2026-01-30 | 2
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Revisão |  | Amarílis Lage de Macedo | A iniciar | 2026-05-17 | 2026-05-27 | 10
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Tradução |  | Amarílis Lage de Macedo | A iniciar | 2026-05-27 | 2026-06-03 | 7
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Anteprojeto básico parcial (áreas 1,2 e 3) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-10-07 | 2025-10-31 | 24
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de detalhamento para conteúdo | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-30 | 2026-05-15 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
ÁREA 4 (crises)
|  |  | Finalização e entrega | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-06-15 | 2026-06-20 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-20 | 2026-07-04 | 45
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-20 | 2026-06-19 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-04-30 | 2026-05-30 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-06-03 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-03 | 2026-06-06 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Cabeamento de lógica e AV |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Chegada e preparo de cabos de rede e dados |  | Racquel Gabriele Prudente e Silva | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-07-14 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Logística e recebimento de equipamentos de som, imagem e rede |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-14 | 2026-06-28 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Instalação |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-03 | 2026-07-23 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Logística e recebimento de equipamentos e materiais |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-20 | 2026-07-04 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Ajustes e entrega final |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-28 | 2026-07-03 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Instalação do conteúdo |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-20 | 2026-06-25 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Testes e acabamentos |  | Amarílis Lage de Macedo | A iniciar | 2026-06-25 | 2026-06-28 | 3
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 4 ¦ VÍDEO ATIVISTAS | Ajustes e entrega final |  | Laura de Paula Rago | A iniciar | 2026-06-29 | 2026-07-09 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 4 ¦ VÍDEO ATIVISTAS | Testes do conteúdo na experiência |  | Laura de Paula Rago | A iniciar | 2026-06-24 | 2026-06-29 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | FOTOS FINE ART ¦ ÁREAS 3 E 4 | Frete |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-03 | 2026-07-10 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | FOTOS FINE ART ¦ ÁREAS 3 E 4 | Montagem |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-10 | 2026-07-15 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | FOTOS FINE ART ¦ ÁREAS 3 E 4 | Produção gráfica |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-03 | 2026-07-03 | 0
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURA EM GUARDACORPO EM DRYWALL EXISTENTE, EM TODA VOLTA DO MEZANINO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-07-09 | 30
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | DEMOLIR FORRO EXISTENTE (GESSO ACARTONADO) ABAIXO DO MEZANINO PARA PASSAGEM DE INFRAESTRUTURAS ELÉTRICAS, DADOS E REFORÇOS ESTRUTURAIS, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | FORRO A CONSTRUIR (GESSO ACARTADONO) ABAIXO DO MEZANINO, COM ACABAMENTO EM PINTURA DE TERRA OU SIMILAR, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-31 | 2026-06-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | CORTINEIRO CORREDOR DA CRISE: ESTRUTURA METÁLICA PARA SUPORTE DE CORTINAS, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | FECHAMENTO PAREDES CURVAS ENTRE ÁREA 0 (CORREDOR) E 4-5: FECHAMENTOS DE PAREDES EM SISTEMA SANDUICHE COMPOSTO POR: FACES INTERNA E EXTERNA DA SALA EM COMPENSADO LAMINADO FLEXÍVEL IMUNIZADO E IGNIFUGADO (APLICADO EM 2 CAMADAS DE 6mm EM PAINÉIS DE 2500X1600) APARAFUSADO SOBRE SUBESTRUTURA EM SISTEMA DE STEELFRAME, APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO PARA VEDAÇÃO DO SISTEMA; MIOLO COM PREENCHIMENTO EM LÃ DE PET DENSIDADE MÍNIMA DE 15KG/M³ (CONFORME PROJETO DE ACÚSTICA). APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO DAS JUNTAS NA FACE INTERNA. FACE VOLTADA PARA ÁREA 0 (CORREDOR) SEM ACABAMENTO E FACE VOLTADA PARA SALAS 4 E 5 COM EMASSAMENTO COMPLETO E PINTURA ACRÍLICA EM COR A DEFINIR. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Içamento e instalação do PATAMAR TÉCNICO AO LONGO DA ÁREA DE PÉ DIREITO DUPLO DA EXPOSIÇÃO, EM ESTRUTURA METÁLICA, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica e redução significativa da área construída de Patamar Técnico, saindo de 357m² para 88m². | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-23 | 2026-06-02 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | PINTURA DE PATAMAR TÉCNICO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-03 | 2026-06-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Conceituação do jogo (desenvolvimento + aprovação) | IZA LESSA | Amarílis Lage de Macedo | Feito | 2026-02-23 | 2026-03-13 | 18
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Contratação Iza Lessa | IZA LESSA | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-03-31 | 60
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Definição de equipamentos e tecnologia do jogo | IZA LESSA | Amarílis Lage de Macedo | Feito | 2026-02-23 | 2026-03-13 | 18
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Desenvolvimento de layout/design | IZA LESSA | Amarílis Lage de Macedo | Atrasado | 2026-03-13 | 2026-04-27 | 45
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Entrega da Região 1 | IZA LESSA | Amarílis Lage de Macedo | Atrasado | 2026-03-23 | 2026-05-08 | 46
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Entrega da Região 2 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-05-08 | 2026-05-22 | 14
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Entrega da Região 3 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-05-22 | 2026-06-03 | 12
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Entrega da Região 4 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-06-03 | 2026-06-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Entrega do Bonikta para Iza | IZA LESSA | Amarílis Lage de Macedo | Feito | 2026-03-13 | 2026-03-23 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Feedback da Região 1 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-05-08 | 2026-05-15 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Feedback da Região 2 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-05-22 | 2026-05-27 | 5
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Feedback da Região 3 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-06-03 | 2026-06-07 | 4
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Feedback da Região 4 | IZA LESSA | Amarílis Lage de Macedo | Definir datas | 2026-06-13 | 2026-06-15 | 2
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Programação / desenvolvimento de software | IZA LESSA | Amarílis Lage de Macedo | Atrasado | 2026-04-27 | 2026-05-08 | 11
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ JOGO "PONTO DE NÃO RETORNO" | Realinhamento do escopo do Bonikta | IZA LESSA | Débora Pires da Silva Rodrigues | Feito | 2026-03-03 | 2026-03-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Alinhamento de Plano de Trabalho | COLETIVO COLETORES | Débora Pires da Silva Rodrigues | Atrasado | 2026-04-25 | 2026-04-30 | 5
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Apresentação do primeiro corte (v1) | COLETIVO COLETORES | Laura de Paula Rago | Risco de atraso | 2026-05-15 | 2026-05-30 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Aprovar a lista de nomes (aprovação interna) | COLETIVO COLETORES | Vitor Garcez de Oliveira | Atrasado | 2026-03-25 | 2026-04-30 | 36
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Briefing e contratação da produtora | COLETIVO COLETORES | Débora Pires da Silva Rodrigues | Atrasado | 2026-04-10 | 2026-04-29 | 19
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Definir lista de ativistas | COLETIVO COLETORES | Laura de Paula Rago | Feito | 2026-03-01 | 2026-03-25 | 24
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Definir pré roteiro do vídeo | COLETIVO COLETORES | Laura de Paula Rago | Feito | 2026-01-29 | 2026-04-10 | 71
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Dispositivo definido com Arquiteutra | COLETIVO COLETORES | Tatiane Baptista Proba Rocha | Feito |  |  | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Montagem - Arquivo Final | COLETIVO COLETORES | Laura de Paula Rago | Risco de atraso | 2026-06-09 | 2026-06-24 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Moodboard/Roteiro | COLETIVO COLETORES | Laura de Paula Rago | Atrasado | 2026-04-30 | 2026-05-15 | 15
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 4 ¦ VÍDEO ATIVISTAS | Produção | COLETIVO COLETORES | Laura de Paula Rago | Risco de atraso | 2026-05-30 | 2026-06-09 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Contratação/Comissionamento |  | Tamires de Figueiredo Pinheiro | Em andamento | 2026-02-23 | 2026-06-03 | 100
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Impressão de fotos |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-13 | 2026-07-03 | 20
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Moldura (definir) |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-03 | 2026-06-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Recebimento de fotos |  | Laura de Paula Rago | Feito | 2026-01-12 | 2026-01-29 | 17
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Recebimento de fotos em alta |  | Débora Pires da Silva Rodrigues | Risco de atraso | 2026-06-03 | 2026-06-13 | 10
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Seleção de artistas |  | Laura de Paula Rago | Feito | 2026-01-16 | 2026-01-16 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS LICENCIADAS | FOTOGRAFIAS ÁREAS 3 E 4 | Seleção final de fotos |  | Laura de Paula Rago | Feito | 2026-01-28 | 2026-01-30 | 2
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Revisão |  | Amarílis Lage de Macedo | A iniciar | 2026-05-17 | 2026-05-27 | 10
PRODUÇÃO DE CONTEÚDO | TEXTOS | LEGENDAS E LEGENDAS EXPANDIDAS | Tradução |  | Amarílis Lage de Macedo | A iniciar | 2026-05-27 | 2026-06-03 | 7
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de detalhamento para conteúdo | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-30 | 2026-05-15 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
ÁREA 5 (bem viver)
|  |  | Recebimento dos equipamentos | LUIZ BRAGA + MARLUS | Débora Pires da Silva Rodrigues | Em andamento | 2026-05-04 | 2026-06-13 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-20 | 2026-07-04 | 45
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-20 | 2026-06-19 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | EQUIPAMENTOS | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-04-30 | 2026-05-30 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-06-03 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | AUTOMAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-06-03 | 2026-06-06 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | TECNOLOGIA | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | Atrasado | 2026-05-15 | 2026-05-18 | 3
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | CÉU DE MIRITI | Aplicação de acabamento na madeira | MIRITI SUSTENTÁVEL | Tatiane Baptista Proba Rocha | Risco de atraso | 2026-05-04 | 2026-05-19 | 15
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | CÉU DE MIRITI | Cotação e contratação | MIRITI SUSTENTÁVEL | Meriene da Cunha Mazzei | Feito | 2026-01-13 | 2026-01-16 | 3
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | CÉU DE MIRITI | Definição do acabamento do material | MIRITI SUSTENTÁVEL | Vitor Garcez de Oliveira | Feito | 2026-04-04 | 2026-05-04 | 30
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | CÉU DE MIRITI | Logística de entrega e recebimento do material | MIRITI SUSTENTÁVEL | Wellington Bruno Soares da Silva | A iniciar | 2026-05-19 | 2026-05-29 | 10
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | CÉU DE MIRITI | Produção do material | MIRITI SUSTENTÁVEL | Tatiane Baptista Proba Rocha | Atrasado | 2026-02-03 | 2026-05-04 | 90
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Cabeamento de lógica e AV |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Chegada e preparo de cabos de rede e dados |  | Racquel Gabriele Prudente e Silva | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Instalação |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-06-14 | 2026-07-14 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Logística e recebimento de equipamentos de som, imagem e rede |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-14 | 2026-06-28 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUDIOVISUAL | Testes e validações |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-14 | 2026-07-24 | 10
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Instalação |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-03 | 2026-07-23 | 50
MONTAGEM DE EXPO DE LONGA | INSTALAÇÃO COMPLEMENTARES | AUTOMAÇÃO | Logística e recebimento de equipamentos e materiais |  | Racquel Gabriele Prudente e Silva | A iniciar | 2026-05-20 | 2026-07-04 | 45
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 5 ¦ BEM VIVER | Ajustes e entrega final |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-04 | 2026-07-10 | 6
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 5 ¦ BEM VIVER | Inclusão de conteúdos da experiência (Fotos e som) |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-19 | 2026-06-24 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 5 ¦ BEM VIVER | Montagem da experiência no museu |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-19 | 2026-07-04 | 15
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 5 ¦ BEM VIVER | Montagem da iluminação interativa |  | Vitor Garcez de Oliveira | A iniciar | 2026-06-19 | 2026-06-29 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 5 ¦ BEM VIVER | Testes de conteúdo e da interação física |  | Vitor Garcez de Oliveira | A iniciar | 2026-07-04 | 2026-07-09 | 5
MONTAGEM DE EXPO DE LONGA | MONTAGEM COM CONTEÚDO | ÁREA 5 ¦ BEM VIVER | Transporte da experiência para Belém |  | Débora Pires da Silva Rodrigues | A iniciar | 2026-06-12 | 2026-06-19 | 7
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação objetos táteis |  | Tatiana Paulino de Azevedo | A iniciar | 2026-06-23 | 2026-07-03 | 10
MONTAGEM DE EXPO DE LONGA | MONTAGEM FINA | ACESSIBILIDADE | Instalação piso podotátil |  | Tatiana Paulino de Azevedo | A iniciar | 2026-07-01 | 2026-07-11 | 10
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | PINTURAS EM ELETROCALHAS, PERFILADO E ELETRODUTOS GALVAZINADOS APARENTES NA ÁREA EXPOSITIVA. COR: CORAL - MARROM BURGUÊS, CONFORME TESTE DE CORES | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RETIRADA DE ELETROCALHAS DOS EQUIPAMENTOS DE A.C. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-04 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURA EM GUARDACORPO EM DRYWALL EXISTENTE, EM TODA VOLTA DO MEZANINO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-07-09 | 30
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | DEMOLIR FORRO EXISTENTE (GESSO ACARTONADO) ABAIXO DO MEZANINO PARA PASSAGEM DE INFRAESTRUTURAS ELÉTRICAS, DADOS E REFORÇOS ESTRUTURAIS, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | ÁREA EXPOSITIVA ¦ FORRO | FORRO A CONSTRUIR (GESSO ACARTADONO) ABAIXO DO MEZANINO, COM ACABAMENTO EM PINTURA DE TERRA OU SIMILAR, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-31 | 2026-06-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | FECHAMENTO PAREDES CURVAS ENTRE ÁREA 0 (CORREDOR) E 4-5: FECHAMENTOS DE PAREDES EM SISTEMA SANDUICHE COMPOSTO POR: FACES INTERNA E EXTERNA DA SALA EM COMPENSADO LAMINADO FLEXÍVEL IMUNIZADO E IGNIFUGADO (APLICADO EM 2 CAMADAS DE 6mm EM PAINÉIS DE 2500X1600) APARAFUSADO SOBRE SUBESTRUTURA EM SISTEMA DE STEELFRAME, APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO PARA VEDAÇÃO DO SISTEMA; MIOLO COM PREENCHIMENTO EM LÃ DE PET DENSIDADE MÍNIMA DE 15KG/M³ (CONFORME PROJETO DE ACÚSTICA). APLICAÇÃO DE FITAS TELADAS E EMASSAMENTO DAS JUNTAS NA FACE INTERNA. FACE VOLTADA PARA ÁREA 0 (CORREDOR) SEM ACABAMENTO E FACE VOLTADA PARA SALAS 4 E 5 COM EMASSAMENTO COMPLETO E PINTURA ACRÍLICA EM COR A DEFINIR. | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Içamento e instalação do PATAMAR TÉCNICO AO LONGO DA ÁREA DE PÉ DIREITO DUPLO DA EXPOSIÇÃO, EM ESTRUTURA METÁLICA, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica e redução significativa da área construída de Patamar Técnico, saindo de 357m² para 88m². | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-23 | 2026-06-02 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | PINTURA DE PATAMAR TÉCNICO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-03 | 2026-06-13 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Pintura de estrutura - TETO CÉU DE MIRITI |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-03 | 2026-06-13 | 10
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | TETO CÉU DE MIRITI: SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO EXPOGRÁFICO E PROJETO ESTRUTURAL. Houve mudança de projeto considerando diminuição do peso da estrutura metálica. Inclusão dos elementos 'reforço estrutural dentro do peitoril'; 'suporte para projetores "escondidos" (Ver Projeto Expográfico: Ampliação do Céu de Miriti). | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-23 | 2026-06-02 | 10
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CÉU DE MIRITI | Instalação do Material | À DEFINIR | jadejares@gmail.com | A iniciar | 2026-06-02 | 2026-06-17 | 15
MONTAGEM DE EXPO DE LONGA | [TR 03] CENOTÉCNICA | INSTALAÇÃO CÉU DE MIRITI | Logística | JOEL | jadejares@gmail.com | A iniciar | 2026-05-19 | 2026-05-24 | 5
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Compra de equipamentos | LUIZ BRAGA + MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-03-31 | 2026-04-09 | 9
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Contratação Consultoria Marlus | LUIZ BRAGA + MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-01-30 | 2026-01-30 | 0
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Contratação Luiz Braga | LUIZ BRAGA + MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-02-02 | 2026-03-24 | 50
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Desenvolvimento da experiência - Versão 1 | LUIZ BRAGA + MARLUS | Laura de Paula Rago | Em andamento | 2026-05-08 | 2026-05-22 | 14
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Desenvolvimento da experiência - Versão 2 | LUIZ BRAGA + MARLUS | Laura de Paula Rago | A iniciar | 2026-05-22 | 2026-05-30 | 8
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Desenvolvimento da trilha sonora | LUIZ BRAGA + MARLUS | Laura de Paula Rago | Em andamento | 2026-05-08 | 2026-05-22 | 14
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Desenvolvimento do conceito | LUIZ BRAGA + MARLUS | Laura de Paula Rago | Feito | 2026-04-29 | 2026-05-08 | 9
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Detalhamento da interação | LUIZ BRAGA + MARLUS | Laura de Paula Rago | Feito | 2026-03-31 | 2026-04-29 | 29
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Entrega final | LUIZ BRAGA + MARLUS | Laura de Paula Rago | A iniciar | 2026-05-30 | 2026-06-12 | 13
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Envio das imagens em Alta Res. e Legendas | LUIZ BRAGA + MARLUS | Laura de Paula Rago | A iniciar | 2026-05-22 | 2026-05-29 | 7
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Lista de equipamentos | LUIZ BRAGA + MARLUS | Débora Pires da Silva Rodrigues | Feito | 2026-03-01 | 2026-03-31 | 30
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Proposta criativa preliminar do Marlus | LUIZ BRAGA + MARLUS | Laura de Paula Rago | Feito | 2026-01-12 | 2026-01-26 | 14
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Protótipo e teste para aprovação | LUIZ BRAGA + MARLUS | Laura de Paula Rago | A iniciar | 2026-06-12 | 2026-07-01 | 19
PRODUÇÃO DE CONTEÚDO | OBRAS COMISSIONADAS | ÁREA 5 ¦ BEM VIVER | Reunião de criação inicial com Marlus, Luiz Braga e IDG | LUIZ BRAGA + MARLUS | Laura de Paula Rago | Feito | 2026-02-20 | 2026-02-20 | 0
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Data limite para revisão dos complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-27 | 2026-02-11 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Diversidade - Revisão Construtiva | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 01 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-27 | 2026-04-03 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega Projeto Executivo Expográfico Detalhado_Parte 02 | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-03 | 2026-04-10 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do detalhamento da expografia | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-28 | 2026-01-28 | 0
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega do projeto expografia revisado (após obs curadoras) | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-29 | 2026-03-06 | 36
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final dos Projetos Executivos Complementares | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-02-03 | 2026-03-13 | 38
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entrega final projeto executivo compatibilizado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-03-27 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Entregas intermediárias - ilum, tec, ar e acústica | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-01-12 | 2026-01-26 | 14
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de detalhamento para conteúdo | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-30 | 2026-05-15 | 15
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Revisão de layout | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-15 | 2026-04-30 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Análise Interna da Exposição Sala a sala |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-20 | 2026-04-24 | 4
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Desenho da estrutura do webapp (Iza Lessa) |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | ACESSIBILIDADE |  | Elaboração de plano de acessibilidade |  | Leandro Guedes Nóbrega de Moraes | Atrasado | 2026-04-24 | 2026-05-09 | 15
PROJETOS COMPLEMENTARES | AUTOMAÇÃO |  | Revisão DMX | SALT | Tatiane Baptista Proba Rocha | Atrasado | 2026-04-17 | 2026-05-07 | 20
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
MEZANINO
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Compra de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-19 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | CFTV |  | Cotação de equipamentos e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Contratação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-04-30 | 2026-05-20 | 20
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Dimensionar quantitativo |  | jadejares@gmail.com | Feito | 2026-04-20 | 2026-04-25 | 5
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Extração do material |  | Gabriela Carvalho | A iniciar | 2026-05-20 | 2026-05-30 | 10
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Logística de envio e recebimento |  | jadejares@gmail.com | A iniciar | 2026-05-30 | 2026-06-09 | 10
COMPRAS E CONTRATAÇÕES ¦ EXPOGRAFIA | MATERIAIS ESPECIAIS | BARROS DO MARAJÓ PARA TINTA | Orçamento |  | Gabriela Carvalho | Feito | 2026-04-25 | 2026-04-30 | 5
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | CHAPIM GUARDA CORPO MEZANINO | ADEQUAÇÃO DO GUARDA CORPO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-23 | 2026-06-07 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | CHAPIM GUARDA CORPO MEZANINO | APLICAÇÃO NO MUSEU - MADEIRA MACIÇA CHAPINS | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-07 | 2026-06-14 | 7
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO DE MADEIRA MACIÇA PARA PISOS E CHAPINS | RCM | Pedro Humberto Santos Rodrigues | Feito | 2026-06-15 | 2026-06-30 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURA EM GUARDACORPO EM DRYWALL EXISTENTE, EM TODA VOLTA DO MEZANINO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-07-09 | 30
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURAS DE PAREDES EM DRYWALL, EXISTENTES DO BANHEIRO DO MEZANINO, EM TINTAS ACRÍLICAS, COR: CINZA SUVINIL, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-01 | 2026-05-31 | 30
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | RECEBIMENTO DA TERRA DO MARAJÓ PARA PREPARO DE TINTA | MÃOS CARUANAS | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-06-09 | 0
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | RECEBIMENTO DE MADEIRA PARA CHAPIM | LA MAPA | Pedro Humberto Santos Rodrigues | Feito | 2026-04-30 | 2026-05-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | DEMANDAS EXTRAS | GUARDA CORPO MEZANINO FOYER: GUARDA CORPO EM VIDRO LAMINADO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Logística de chegada da madeira | RCM | Gabriela Carvalho | Feito | 2026-04-27 | 2026-05-04 | 7
PROJETO EXPOGRÁFICO | PROJETO EXECUTIVO |  | Projeto Executivo Arquitetônico Detalhado | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2026-04-10 | 2026-04-15 | 5
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Adicionais de áreas de circulação | FERNANDA CARVALHO |  | Em andamento | 2026-05-12 | 2026-05-19 | 7
EXPOSIÇÃO TEMPORÁRIA
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | RECEBIMENTO DE MADEIRA PARA CHAPIM | LA MAPA | Pedro Humberto Santos Rodrigues | Feito | 2026-04-30 | 2026-05-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Cabeamento de elétrica | À DEFINIR | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-31 | 17
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
LOJA
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURAS DE PAREDES E TETO EM DRYWALL, EXISTENTES NA LOJA | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-09 | 2026-06-24 | 15
PROJETO EXPOGRÁFICO | ANTEPROJETO |  | Revisão do anteprojeto | BE.BO E GUÁ | Tatiane Baptista Proba Rocha | Feito | 2025-12-16 | 2025-12-19 | 3
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Revisão do projeto executivo | FERNANDA CARVALHO | Tatiane Baptista Proba Rocha | Feito | 2026-03-13 | 2026-05-12 | 60
ÁREA EXTERNA DO MUSEU
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | AD |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | espanhol |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | inglês |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | CONTEÚDO AUDIOGUIA | libras |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-18 | 40
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis das experiências |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Fabricação das peças táteis dos totens |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-08 | 2026-06-23 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PRODUÇÃO DE PEÇAS TÁTEIS | Mapas táteis |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-05-09 | 2026-06-08 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | CHAPIM GUARDA CORPO MEZANINO | APROVAÇÃO DE ORÇAMENTO - BENEFICIAMENTO DE MADEIRA | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-20 | 2026-05-21 | 1
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | CHAPIM GUARDA CORPO MEZANINO | BENEFICIAMENTO DA MADEIRA MACIÇA PARA CHAPINS DE GUARDA-CORPOS - BENEFICIAMENTO DA MADEIRA | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-23 | 2026-06-07 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | CHAPIM GUARDA CORPO MEZANINO | TRANSPORTE PARA MARCENARIA | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-21 | 2026-05-23 | 2
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Aquisição do material da DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-07 | 2026-05-18 | 11
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Fabricação em galpão TETO CÉU DE MIRITI | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-01 | 2026-05-20 | 19
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Fabricação da estrutura da DIVERSIDADE em galpão | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-18 | 2026-06-07 | 20
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Fabricação do Patamar técnico em galpão | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-01 | 2026-05-20 | 19
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Transporte do material para o museu | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-20 | 2026-05-22 | 2
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Transporte do material para o museu | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-08 | 2026-06-09 | 1
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRTUTURA ¦ TETO | Transporte do material para o museu - TETO CÉU DE MIRITI | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-20 | 2026-05-22 | 2
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | Aquisição do material da DIVERSIDADE PAREDES CURVAS E ESPIRA | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-07 | 2026-05-18 | 11
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | Fabricação em galpão - DIVERSIDADE PAREDES CURVAS E ESPIRA | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-18 | 2026-06-07 | 20
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PAREDES | Transporte do material para o museu DIVERSIDADE PAREDES CURVAS E ESPIRA | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-06-08 | 2026-06-09 | 1
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | ESTRUTURA ¦ PISO | Aquisição de insumos - PINGUELA, DIVERSIDADE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-20 | 2026-05-21 | 1
MONTAGEM DE EXPO DE LONGA | [TR 02] ESTRUTURAS DA EXPOGRAFIA | FECHAMENTO ¦ PISO | Logística de chegada da madeira | RCM | Gabriela Carvalho | Feito | 2026-04-27 | 2026-05-04 | 7
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
ÁREAS COMUNS (BNHS, CIRCULAÇÕES ETC.)
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES |  |  | Cotação de adequações | PROMEC | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-14 | 2026-05-29 | 15
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Contratação de fornecedor |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-18 | 2026-06-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Cotação para fornecimento de material e instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-06-08 | 2026-06-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ACESSIBILIDADE | PISO PODOTÁTIL | Plano de execução e cronograma de instalação |  | Leandro Guedes Nóbrega de Moraes | A iniciar | 2026-06-28 | 2026-07-01 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Contratação de adequação do projeto de combate a incêndio para as exposições novas | PROMEC | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-14 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ADEQUAÇÃO DO SISTEMA CONTRA INCÊNDIO |  | Cotação e contratação de fornecedor para instalar sistema de detectores de fumaça e alarme | PREVENÇÃO | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-02 | 2026-05-11 | 70
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | Risco de atraso | 2026-05-09 | 2026-05-29 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-04 | 2026-05-09 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ELÉTRICA |  | Definir plano de trabalho com fornecedor |  | Tatiane Baptista Proba Rocha | A iniciar | 2026-05-09 | 2026-05-14 | 5
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-17 | 2026-06-06 | 20
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Cotação dos serviços |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-04-17 | 2026-05-17 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | INSTALAÇÃO | Definir plano de trabalho com fornecedor |  | Gabriela Carvalho | A iniciar | 2026-06-06 | 2026-06-09 | 3
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Chegada dos materiais |  | jadejares@gmail.com | A iniciar | 2026-05-22 | 2026-06-21 | 30
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Compra de lumináriase materiais |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-12 | 2026-05-22 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | ILUMINAÇÃO | LUMINÁRIAS | Cotação de luminárias e materiais |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-03-13 | 2026-05-12 | 60
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Contratação da instalação |  | Claire Beatriz Barbosa da Silva Muniz | A iniciar | 2026-05-18 | 2026-05-28 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Cotação dos serviços e equipamentos |  | Claire Beatriz Barbosa da Silva Muniz | Atrasado | 2026-05-08 | 2026-05-18 | 10
COMPRAS E CONTRATAÇÃO ¦ COMPLEMENTARES | SISTEMA DE CLIMATIZAÇÃO |  | Definir plano de trabalho com fornecedor |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-28 | 2026-05-30 | 2
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Compatibilização de projeto com exposição de longa | PROMEC | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-04 | 2026-05-14 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação de luzes de emergência e sinalização de fuga |  | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-29 | 2026-06-28 | 30
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Instalação dos sensores e alarmes | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-11 | 2026-05-26 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADEQUAÇÃO SIST. SEGURANÇA CONTRA INCÊNDIO | Mobilização e compra de material | PREVENÇÃO | Pedro Humberto Santos Rodrigues | Atrasado | 2026-05-14 | 2026-05-29 | 15
MONTAGEM DE EXPO DE LONGA | INSTALAÇÕES ESPECIAIS | ADESIVAGEM DOS VIDROS | Execução | RG | Wellington Bruno Soares da Silva | Em andamento | 2026-03-30 | 2026-05-19 | 50
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | FORNECIMENTO E APLICAÇÃO DE RESINA PARA GRANILITE, CONFORME ESPECIFICAÇÃO TÉCNICA DO FABRICANTE | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-30 | 2026-06-14 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | DEMANDAS EXTRAS | RESTAURAÇÃO EM ESCADAS EXISTENTES; RETOQUES COM MASSA AUTOMOTIVA EM SOLDAS E ABERTURAS, EMASSAMENTO ACRÍLICO COMPLETO E ACABAMENTO EM PINTURA ESMALTE SINTÉTICO, COR: VERMELHO ESPECIFICADO IN LOCO | RCM | Pedro Humberto Santos Rodrigues | Em andamento | 2026-05-15 | 2026-05-30 | 15
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | PINTURAS DE PAREDES EXISTENTES DO BANHEIRO DO TÉRREO, EM TINTAS ACRÍLICAS, COR: CINZA SUVINIL, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-13 | 2026-05-18 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ACABAMENTOS | RECEBIMENTO DE MADEIRA PARA CHAPIM | LA MAPA | Pedro Humberto Santos Rodrigues | Feito | 2026-04-30 | 2026-05-05 | 5
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | FOYER, LOJA, MEZANINO ¦ ESQUADRIAS | FORNECIMENTO E INSTALAÇÃO DE PORTA AUTOMÁTICA PARA ENTRADA PRINCIPAL, EM PERFIL METÁLICO E FOLHAS DE VIDRO, 3,8 X 2,82m, CONFORME PROJETO | RCM | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-25 | 2026-06-15 | 21
MONTAGEM DE EXPO DE LONGA | [TR 01] OBRAS CIVÍS | INSTALAÇÕES ELÉTRICAS | Quadros de luz | À DEFINIR | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-31 | 2026-06-15 | 15
PROJETOS COMPLEMENTARES | ELÉTRICA |  | Revisão DMX; Combate ao Incêndio; A/C (talvez); Expo Temporária; Sala Multi | FERNANDO | Tatiane Baptista Proba Rocha | Em andamento | 2026-04-20 | 2026-05-18 | 28
PROJETOS COMPLEMENTARES | ILUMINAÇÃO |  | Adicionais de áreas de circulação | FERNANDA CARVALHO |  | Em andamento | 2026-05-12 | 2026-05-19 | 7

## Contatos
Nomes | E-mails
Exposições e Projetos | exposicoeseprojetos@idg.org.br
Pedro Humberto Santos Rodrigues | pedro.rodrigues@idg.gov.br
jadejares@gmail.com | jadejares@gmail.com
Ana Carolina Peixoto | anacarolina.peixoto@idg.org.br
Racquel Gabriele Prudente e Silva | racquel.prudente@idg.org.br
Tatiana Paulino de Azevedo | tatiana.azevedo@idg.org.br
Vitor Garcez de Oliveira | vitor.garcez@idg.org.br
Sergio Mendes | sergioe.mendes@idg.org.br
Tatiane Baptista Proba Rocha | tatiane.proba@idg.org.br
Meriene da Cunha Mazzei | mariene.mazzei@idg.org.br
Gabriela Carvalho | gabriela.carvalho@idg.org.br
Débora Pires da Silva Rodrigues | debora.pires@idg.org.br
Amarílis Lage de Macedo | amarilis.macedo@idg.org.br
Laura de Paula Rago | laura.rago@idg.org.br
Iago Gonçalves Pereira | iago.pereira@idg.org.br
Jomara Ferreira Chaves Santos | jomara.santos@idg.org.br
Luiz Brasil Borbo Rodrigues Junior | luiz.brasil@idg.org.br
Leandro Guedes Nóbrega de Moraes | leandro.moraes@idg.org.br
Wellington Bruno Soares da Silva | wellington.soares@idg.org.br
Claire Beatriz Barbosa da Silva Muniz | claire.muniz@idg.org.br
Beatriz Costa de Melo | beatriz.melo@idg.org.br
Camila da Silva Costa | camila.costa@idg.org.br
Gabriele de Oliveira Martins | gabriele.martins@idg.org.br
Marina Piquet | marina.piquet@idg.org.br
Tamires de Figueiredo Pinheiro | tamires.figueiredo@idg.org.br
francofguilherme@gmail.com | francofguilherme@gmail.com

## Cópia cronograma SM v24-04-2026 (hidden)
[6 empty] | REPACTUAÇÃO - 24/04 |  |  | PREDECESSORES | BASELINE 28/02 |  |  | ATUALIZAÇÃO QUI, 12/03/2026 |  |  | ATUALIZAÇÃO QUI, 19/03/2026 |  |  | ATUALIZAÇÃO QUI, 26/03/2026 |  |  | ATUALIZAÇÃO QUI, 02/04/2026 |  |  | ATUALIZAÇÃO SEG, 13/04/2026 |  |  | ATUALIZAÇÃO QUI, 16/04/2026 |  |  | ATUALIZAÇÃO SEX, 24/04/2026
Eixo | Grupo | Marco (Entregável) | Tarefa | Responsável | Status | Data Início | Data Fim | Duração | Predecessores | Data Início | Data Fim | Duração | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação | PROGRESSO - O Que Andou Na Última Semana | IMPACTO - Riscos e Problemas | ENCAMINHAMENTOS - Plano de Ação
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | FORRO | DEMOLIR FORRO EXISTENTE (GESSO ACARTONADO) ABAIXO DO MEZANINO PARA PASSAGEM DE INFRAESTRUTURAS ELÉTRICAS, DADOS E REFORÇOS ESTRUTURAIS, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25 | [19 empty] | Está perto da data fim, porém, será finalizado no prazo. | Não há. | Continuação do serviço.
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | FORRO | FORRO A CONSTRUIR (GESSO ACARTADONO) ABAIXO DO MEZANINO, COM ACABAMENTO EM PINTURA DE TERRA OU SIMILAR, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-05-31 | 30 |  | 2026-03-17 | 2026-04-01 | 15 | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | [13 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA E REFRIGERAÇÃO ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | FORRO | FORRO A CONSTRUIR (GESSO ACARTADONO) ABAIXO DA ESCADA, COM ACABAMENTO EM PINTURA ACRÍLICA, COR: BRANCO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-05-31 | 30 |  | 2026-03-17 | 2026-04-01 | 15 | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | [13 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA E REFRIGERAÇÃO ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | PAREDES E PAINÉIS | PAREDES DE DRYWALL COM 10cm DE ESPESSURA PARA CRIAÇÃO DE ÁREA TÉCNICA COM PORTA DE ACESSO ABAIXO DA ESCADA NO TÉRREO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25 |  | 2026-03-17 | 2026-04-01 | 15 | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | PISO | DEMOLIR PISO EXISTENTE EM PORCELANATO MICRON BEGE, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25 |  | 2026-03-17 | 2026-04-01 | 15 | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | PISO | ASSENTAR PISOS CIMENTÍCIOS FEITOS SOB ENCOMENDA, TIPO GRANILITE, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-04-16 | 2026-05-31 | 45 |  | 2026-03-17 | 2026-04-01 | 15 | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | Projeto apresentado e enviado em 13/03 | Depende do envio do projeto de infra que passará pelo piso que precisa ser alinhado com todos os complementares. | Iniciar o serviço | [13 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO E LOGICA ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | INFRAESTRUTURA | EXECUÇÃO DE INFRAESTRUTURA PARA CABEAMENTOS DE ELÉTRICA; INCLUINDO ABERTURA DE ACESSO PELO CHÃO E INSTALAÇÃO DE ELETRODUTOS, CONFORME ESTIMATIVA DE PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-04-16 | 2026-05-15 | 29 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | INFRAESTRUTURA | EXECUÇÃO DE INFRAESTRUTURA PARA CABEAMENTOS DE LÓGICA; INCLUINDO ABERTURA DE ACESSO PELO CHÃO E INSTALAÇÃO DE ELETRODUTOS, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-04-16 | 2026-05-15 | 29 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | INFRAESTRUTURA | EXECUÇÃO DE INFRAESTRUTURA DE HIDRÁULICA; INCLUINDO ABERTURA DE ACESSO PELO CHÃO E EXECUÇÃO DE PONTOS E DESLOCAMENTO DE 1 HIDRANTE EXISTENTE, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-04-16 | 2026-05-15 | 29 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ESQUADRIAS | PORTA DE GIRO EM MADEIRA, 0,80x2,10m, COR: A DEFINIR, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-16 | 2026-05-31 | 15 |  | 2026-03-17 | 2026-04-01 | 15 | Verificada a necessidade de pintura | – | Garcez em Belém na semana que vem, vai bater o martelo na cor a ser usada. | Verificada a necessidade de pinturane definida a técnica a ser usada. | – | Definir cor | [9 empty] | Foi iniciado o emassamento, a pintura só será finalizada próximo da data de reabertura do museu. |  | Indicar como data final 15/06 |  | AGUARDANDO O DETALHAMENTO DO PROJETO E A EXECUÇÃO DA PAREDE PARA INSTALAÇÃO
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ESQUADRIAS | PORTA DE GIRO EM PCF, 2 FOLHAS, 1,50x2,10, COR: A DEFINIR, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-16 | 2026-05-31 | 15 |  | 2026-03-17 | 2026-04-01 | 15 | Testes realizados. material ok para receber pintura | – | Garcez em Belém na semana que vem, vai bater o martelo na cor a ser usada. | Dutos em pintura | – | Finalização da atividade | [9 empty] | Foi verificado, após o pedido de cotação que o prazo entrega do material é de 60 dias. A produção Gabriela Carvalho está verificando a possibilidade | Esse material é usado para área 0, 1 e 2. A falta do item inviabiliza a abertura da exposição | - Pedro irá visitar o fornecedor entre os dias 17/04 e 20/04. - Aguardando retorno da arquitetura. |  | AGUARDANDO O DETALHAMENTO DO PROJETO E A EXECUÇÃO DA PAREDE PARA INSTALAÇÃO
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | PINTURAS DE PAREDES EXISTENTES NA ÁREA EXPOSITIVA DO TÉRREO EM TINTAS DE TERRA, COR: BARRO/ A DEFINIR, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDANDO SE SERÁ POSSIVEL NA PRESENTE DATA O QUANTITATIVO DE ''BARRO'' PARA EXECUÇÃO DO SERVIÇO OU SE SERÁ REALIZADA OUTRO TIPO DE PINTURA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | PINTURAS EM TETOS DE DRYWALL A CONSTRUIR NA ÁREA EXPOSITIVA E LOJA DO TÉRREO EM TINTAS DE TERRA, COR: BARRO/ A DEFINIR, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA E REFRIGERAÇÃO ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | PINTURAS DE PAREDES EXISTENTES E A CONSTRUIR, PINTURA EM TINTAS DE TERRA, COR: PRETA/ TEXTURA TIPO CARVÃO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA E REFRIGERAÇÃO ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | PINTURAS EM TETOS EXISTENTES E A CONSTRUIRNA ÁREA EXPOSITIVA DO TÉRREO EM TINTAS DE TERRA, COR: PRETA/ TEXTURA TIPO CARVÃO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO, LOGICA E REFRIGERAÇÃO ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | PINTURAS EM DUTOS EXISTENTES DE AR CONDICIONADO, COR: VERMELHO ÓXIDO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | REMOÇÃO DE PINTURA EM ESCADAS METÁLICAS EXISTENTES | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | PINTURA EM ESCADAS METÁLICAS EXISTENTES, COR: VERMELHO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-16 | 2026-05-31 | 15
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | FORNECIMENTO E FIXAÇÃO DE ESPELHO EM TETO EXISTENTE DE DRYWALL, CONFORME PROJETO - OBS: GEOMETRIA ORGÂNICA DO FOYER | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-01 | 2026-05-31 | 30
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | PAREDES E PAINÉIS | AJUSTE E DIMINUIÇÃO DOS MONTANTES DE GUARDA CORPO EXISTENTE, ENTRE O MEZANINO E FOYER, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-04-26 | 25
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | PAREDES E PAINÉIS | PAREDES DE DRYWALL COM 10cm DE ESPESSURA PARA CRIAÇÃO DE HALL PARA BANHEIRO EXISTENTE NO TÉRREO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-05-31 | 30 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO E LOGICA ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | PISO | DEMOLIR PISO EXISTENTE EM GRANILITE MONOLÍTICO VERMELHO | Pedro Humberto Santos Rodrigues | Feito | 2026-05-01 | 2026-05-31 | 30
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | PISO | ASSENTAR PISOS CIMENTÍCIOS FEITOS SOB ENCOMENDA, TIPO GRANILITE, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-04-16 | 2026-05-31 | 45 | [23 empty] | AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO E LOGICA ( POREM PODE EXECUTAR ALGUNS TRECHOS)
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ESQUADRIAS | FORNECIMENTO E INSTALAÇÃO DE PORTA AUTOMÁTICA PARA ENTRADA PRINCIPAL, EM PERFIL METÁLICO E FOLHAS DE VIDRO, 3,8 X 2,82m, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-01 | 2026-05-15 | 14
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | PINTURAS DE PAREDES E TETO EM DRYWALL, EXISTENTES NA LOJA EM TINTAS DE TERRA, COR: BARRO AMARELO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDANDO SE SERÁ POSSIVEL NA PRESENTE DATA O QUANTITATIVO DE ''BARRO'' PARA EXECUÇÃO DO SERVIÇO OU SE SERÁ REALIZADA OUTRO TIPO DE PINTURA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | PINTURAS DE PAREDES E TETO EM DRYWALL, EXISTENTES NO FOYER EM TINTAS DE TERRA, COR: BARRO VERMELHO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDANDO SE SERÁ POSSIVEL NA PRESENTE DATA O QUANTITATIVO DE ''BARRO'' PARA EXECUÇÃO DO SERVIÇO OU SE SERÁ REALIZADA OUTRO TIPO DE PINTURA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | PINTURA EM GUARDACORPO EM DRYWALL EXISTENTE, EM TODA VOLTA DO MEZANINO, EM PINTURA DE TERRA, COR: BARRO AMARELO, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDANDO SE SERÁ POSSIVEL NA PRESENTE DATA O QUANTITATIVO DE ''BARRO'' PARA EXECUÇÃO DO SERVIÇO OU SE SERÁ REALIZADA OUTRO TIPO DE PINTURA
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | PINTURAS DE PAREDES EM DRYWALL, EXISTENTES DO BANHEIRO DO MEZANINO, EM TINTAS ACRÍLICAS, COR: CINZA SUVINIL, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-01 | 2026-05-31 | 30
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | PINTURAS DE PAREDES EXISTENTES DO BANHEIRO DO TÉRREO, EM TINTAS ACRÍLICAS, COR: CINZA SUVINIL, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | A iniciar | 2026-05-01 | 2026-05-31 | 30
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | INSTALAÇÃO DE CHAPIM PARA GUARDACORPO EXISTENTE EM TODA VOLTA DO MEZANINO, EM MADEIRA CERTIFICADA, COR: A DEFINIR, CONFORME PROJETO - OBS: Madeira fornecida pela CONTRATANTE CONFORME ESPECIFICADO EM EDITAL. | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-05-15 | 14 | [23 empty] | AGUARDANDO O ORÇAMENTO DA LA MAPA E DEFINICIÇÃO DE QUEM IRÁ FAZER A AQUISIÇÃO DO INSUMO
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ELÉTRICA | INSTALAÇÕES ELÉTRICAS |  | Pedro Humberto Santos Rodrigues | A iniciar
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | TETO | PATAMAR TÉCNICO AO LONGO DA ÁREA DE PÉ DIREITO DUPLO DA EXPOSIÇÃO, EM ESTRUTURA METÁLICA EM PERFIS "I" SUSPENSOS NA ESTRUTURA EXISTENTE DO GALPÃO + PISO METÁLICO VAZADO 30MM, CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL. | Pedro Humberto Santos Rodrigues | Em andamento | 2026-04-01 | 2026-05-31 | 60
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | TETO | TETO DA ESPIRAL ESTRUTURADAS POR TUBOS METÁLICOS FIXADOS NA ESTRUTURA PRINCIPAL DAS PAREDES E SUSPENSOS NA ESTRUTURA METÁLICA EXISTENTE DO GALPÃO. VERIFICAR PROJETO ESTRUTURAL. | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-16 | 2026-05-31 | 15 | [23 empty] | AGUARDANDO O PROJETO EXECUTIVO RO.DA ( ENG RODRIGO ) - PRAZO DE EXECUÇÃO: 15 DIAS - APÓS RECEBIMENTO DO PROJETO!
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | TETO | TETO DA ORALIDADE: SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL. | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-06-01 | 2026-06-15 | 14 | [23 empty] | AGUARDANDO O PROJETO EXECUTIVO RO.DA ( ENG RODRIGO ) - PRAZO DE EXECUÇÃO: 10 DIAS - APÓS RECEBIMENTO DO PROJETO!
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | TETO | TETO CÉU DE MIRITI: SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL. | Pedro Humberto Santos Rodrigues | Em andamento | 2026-04-01 | 2026-05-15 | 44 | [23 empty] | AGUARDO DO ENVIO DO PROJETO - 07/04/2026
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | PAREDES | PAREDES CURVAS E ESPIRAL: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL E TRECHO DE PAREDES SUSPENSAS | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-15 | 2026-05-31 | 16 | [23 empty] | AGUARDANDO O PROJETO EXECUTIVO RO.DA ( ENG RODRIGO ) - PRAZO DE EXECUÇÃO: 30 DIAS - APÓS RECEBIMENTO DO PROJETO!
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | PAREDES | ORALIDADE: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO ESTRUTURAL + FECHAMENTO EM CHAPAS DE COMPENSADO, NÚCLEO PREENCHIDO COM ISOLAMENTO ACÚSTICO A SER DEFINIDO. CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-05-15 | 44
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | PAREDES | ATURÁ: PAREDES COM SISTEMA MISTO EM ESTRUTURA METÁLICA COM PERFIS TUBULARES MECÂNICOS E CHAPAS, CONFORME PROJETO ESTRUTURAL. VERIFICAR PROJETO ESTRUTURAL. | Pedro Humberto Santos Rodrigues | Feito | 2026-04-01 | 2026-05-15 | 44
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | PISO | PINGUELA E ÁREAS TÉCNICAS EM PISO EXECUTADO COMO SISTEMA ELEVADO EM ESTRUTURA COM BASE METÁLICA, CONFORME PROJETO. VERIFICAR PROJETO ESTRUTURAL. | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-05-01 | 2026-06-15 | 45 | [23 empty] | AGUARDAR O DETALHAMENTO DA ARQUITETURA ( ALVENARIA E O PAINEL WALL ''FECHAMENTO'' ) / VALIDAÇÃO DA LOCAÇÃO(TRACEJADO) NO PISO DO GALPÃO / DEFINIR COMO SERÁ AQUISIÇÃO DA MADEIRA DO DECK ( LA MAPA) / AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO E LOGICA ( POREM PODE EXECUTAR SIMULTANEAMENTE) - PRAZO DE EXECUÇÃO: 40 DIAS - APÓS DEFINIÇÕES
MONTAGEM DE EXPO DE LONGA | (TR 2) ESTRUTURAS DA EXPOGRAFIA | PISO | PISO DA ORALIDADE EM SISTEMA DE PISO ELEVADO SOBRE O PISO EXISTENTE, CONFORME PROJETO | Pedro Humberto Santos Rodrigues | Risco de atraso | 2026-04-01 | 2026-05-31 | 60 | [23 empty] | AGUARDAR O DETALHAMENTO DA ARQUITETURA ( ALVENARIA E O PAINEL WALL ''FECHAMENTO'' ) / DEFINIR COMO SERÁ AQUISIÇÃO DA MADEIRA DO DECK ( LA MAPA) / AGUARDAR A COMPATIBILIZAÇÃO DO PROJETO DE INFRA ELETRICA, SONORIZAÇÃO E LOGICA ( POREM PODE EXECUTAR SIMULTANEAMENTE) - PRAZO DE EXECUÇÃO: 20 DIAS - APÓS DEFINIÇÕES
Formulas:
Data Fim = [Duração]+[BASELINE 28/02]

## Tabela dinâmica 6 (hidden)
Eixo | Grupo | Marco (Entregável) | Data Início | Data Fim | Status
MONTAGEM DE EXPO DE LONGA | (TR 1) OBRAS CIVIS - ÁREA EXPOSITIVA | ACABAMENTOS | 2026-04-01 | 2026-04-26 | Feito
|  |  | 2026-05-01 | 2026-05-31 | A iniciar
|  |  |  | 2026-06-15 | Risco de atraso
|  |  | 2026-05-16 | 2026-05-31 | A iniciar
|  | ESQUADRIAS | 2026-05-16 | 2026-05-31 | Risco de atraso
|  | FORRO | 2026-04-01 | 2026-04-26 | Feito
|  |  | 2026-05-01 | 2026-05-31 | Risco de atraso
|  | INFRAESTRUTURA | 2026-04-16 | 2026-05-15 | Risco de atraso
|  | PAREDES E PAINÉIS | 2026-04-01 | 2026-04-26 | Feito
|  | PISO | 2026-04-01 | 2026-04-26 | Feito
|  |  | 2026-04-16 | 2026-05-31 | Risco de atraso
| (TR 1) OBRAS CIVIS - ELÉTRICA | INSTALAÇÕES ELÉTRICAS | (vazio) | (vazio) | A iniciar
| (TR 1) OBRAS CIVIS - FOYER, LOJA, MEZANINO | ACABAMENTOS | 2026-05-01 | 2026-05-15 | Risco de atraso
|  |  |  | 2026-05-31 | A iniciar
|  |  |  | 2026-06-15 | Risco de atraso
|  | ESQUADRIAS | 2026-05-01 | 2026-05-15 | A iniciar
|  | PAREDES E PAINÉIS | 2026-04-01 | 2026-04-26 | Feito
|  |  | 2026-05-01 | 2026-05-31 | Risco de atraso
|  | PISO | 2026-04-16 | 2026-05-31 | Risco de atraso
|  |  | 2026-05-01 | 2026-05-31 | Feito
| (TR 2) ESTRUTURAS DA EXPOGRAFIA | PAREDES | 2026-04-01 | 2026-05-15 | Feito
|  |  | 2026-05-15 | 2026-05-31 | Risco de atraso
|  | PISO | 2026-04-01 | 2026-05-31 | Risco de atraso
|  |  | 2026-05-01 | 2026-06-15 | Risco de atraso
|  | TETO | 2026-04-01 | 2026-05-15 | Em andamento
|  |  |  | 2026-05-31 | Em andamento
|  |  | 2026-05-16 | 2026-05-31 | Risco de atraso
|  |  | 2026-06-01 | 2026-06-15 | Risco de atraso
(vazio)